## Sprint-wise Backlog
S.NO. | Sprint No. | Labels | Key | Component/s | Fix Version/s | Res | Status | Last Dev User | Last QA User | Remarks | Carried Over From | Reason | Estimated Size (in Points) | Revised Size (in Points) | Actual Size (in Points) | Estimated Effort (Days) | Actual Effort (Days)
1 |  | impetus | DEV-30628 | Admin Tools Problem List | 7.4.0 | Verified | Closed | Praveen Kumar | Swati Narang
2 |  | impetus | DEV-27947 | Admin Tools Upgrades | 7.4.0 | Verified | Closed | Kumar Saurabh | Swati Narang
3 |  | impetus | DEV-27573 | Admin Tools Charge Capture | 7.4.0 | Verified | Closed | Sameer Panda | Nitin Anand
4 |  | impetus | DEV-26241 | Admin Tools | 7.4.0 | Verified | Closed | Abhishek Kumar | Swati Narang
5 |  | impetus | DEV-16578 | Admin Tools | 7.4.0 | Verified | Closed | Kumar Saurabh | Nitin Anand
6 |  | impetus_providerdirectory | DEV-32022 | Provider Directory | 7.4.0 | Verified | Closed | Sameer Panda | Swati Narang
7 |  | impetus_providerdirectory | DEV-31997 | Provider Directory | 7.4.0 | Verified | Closed | Praveen Kumar | Nitin Anand
8 |  | impetus_providerdirectory | DEV-31994 | Provider Directory | 7.4.0 | Verified | Closed | Praveen Kumar | Swati Narang
9 |  | impetus_providerdirectory | DEV-31990 | Provider Directory | 7.4.0 | Verified | Closed | Abhishek Kumar | Nitin Anand
10 |  | impetus_providerdirectory | DEV-31989 | Provider Directory | 7.4.0 | Verified | Closed | Abhishek Kumar | Swati Narang
1 | 1 | impetus_sprint01 | DEV-32003 | Admin Tools | 7.4.0 | Not Reproducible | Closed | Praveen Kumar
2 | 1 | impetus_sprint01 | DEV-31993 | Provider Directory | 7.4.0 | Verified | Closed | Praveen Kumar | Nitin Anand
3 | 1 | impetus_sprint01 | DEV-31714 | Charge Capture | 7.4.0 | Known Issue | Closed | Praveen Kumar
4 | 1 | impetus_sprint01 | DEV-31529 | Physician Portal | 7.4.0 | Not Reproducible | Closed | Sameer Panda | Nitin Anand
5 | 1 | impetus_sprint01 | DEV-31242 | Physician Portal Security | Declined Issues | Obsolete | Closed | Sameer Panda
6 | 1 | impetus_sprint01 | DEV-31240 | Physician Portal | 7.4.0 | Duplicate | Closed | Sameer Panda
7 | 1 | impetus_sprint01 | DEV-30932 | Admin Tools | 7.4.0 | Verified | Closed | Kumar Saurabh | Nitin Anand
8 | 1 | impetus_sprint01 | DEV-30911 | Charge Capture | 7.4.0 | Verified | Closed | Abhishek Kumar | Swati Narang
9 | 1 | impetus_sprint01 | DEV-30787 | Charge Capture CPOE | 7.4.0 | Not Reproducible | Closed | Sameer Panda
10 | 1 | impetus_sprint01 | DEV-30339 | Desktop Clinical Results | 7.4.0 | Verified | Closed | Abhishek Kumar | Nitin Anand
11 | 1 | impetus_sprint01 | DEV-30078 | Charge Capture | 7.4.0 | Not Reproducible | Closed | Praveen Kumar | Nitin Anand
12 | 1 | impetus_sprint01 | DEV-29923 | Other (not included in this list) | 7.4.0 | Verified | Closed | Abhishek Kumar | Nitin Anand
13 | 1 | impetus_sprint01 | DEV-28194 | Patient List Mgmt | 7.4.0 | Verified | Closed | Praveen Kumar | Nitin Anand
14 | 1 | impetus_sprint01 | DEV-27364 | Physician Portal | 7.4.0 | Obsolete | Closed | Sameer Panda
15 | 1 | impetus_sprint01 | DEV-22693 | System/Mobilizer | 7.4.0 | Not Reproducible | Closed | Sameer Panda | Nitin Anand
16 | 1 | impetus_sprint01 | DEV-21686 | Forms | 7.4.2 | Verified | Final Review | Praveen Kumar | Swati Narang
17 | 1 | impetus_sprint01 | DEV-15049 | Admin Tools Patient List | 7.4.0 | Verified | Closed | Sameer Panda | Swati Narang
18 | 1 | impetus_sprint01 | DEV-12554 | Admin Tools | Declined Issues | Not Reproducible | Closed | Sameer Panda | Nitin Anand
19 | 1 | impetus_sprint01 | DEV-9329 | Admin Tools | 7.4.0 | Not Reproducible | Closed | Praveen Kumar
20 | 1 | impetus_sprint01 | DEV-9314 | Provider Directory | 7.4.0 | Declined | Closed | Praveen Kumar
1 | 2 | impetus_sprint02 | DEV-32375 | Charge Capture | 7.4.0 | Verified | Closed | Suhani Aneja | Swati Narang
2 | 2 | impetus_sprint02 | DEV-32335 | Admin Tools | 7.4.0 | Verified | Closed | Praveen Kumar | Swati Narang
3 | 2 | impetus_sprint02 | DEV-31682 | Charge Capture Physician Portal | 7.4.0 | Not Reproducible | Closed | Praveen Kumar | Nitin Anand
4 | 2 | impetus_sprint02 | DEV-30707 | Desktop Clinical Results | 7.4.0 | Verified | Closed | Sameer Panda | Swati Narang
5 | 2 | impetus_sprint02 | DEV-30690 | Patient List | 7.4.0 | Verified | Closed | Suhani Aneja | Nitin Anand
6 | 2 | impetus_sprint02 | DEV-30649 | Charge Capture | 7.4.0 | Verified | Closed | Praveen Kumar | Nitin Anand
7 | 2 | impetus_sprint02 | DEV-30576 | Charge Capture | 7.4.0 | Verified | Closed | Kumar Saurabh | Nitin Anand
8 | 2 | impetus_sprint02 | DEV-29288 | Charge Capture | Declined Issues | Working as designed | Closed | Abhishek Kumar
9 | 2 | impetus_sprint02 | DEV-28930 | Charge Capture | 7.4.0 | Verified | Closed | Praveen Kumar | Nitin Anand
10 | 2 | impetus_sprint02 | DEV-28818 | Charge Capture | 7.4.0 | Verified | Closed | Abhishek Kumar | Swati Narang
11 | 2 | impetus_sprint02 | DEV-27744 | Charge Capture | 7.4.0 | Verified | Closed | Abhishek Kumar | Nitin Anand
12 | 2 | impetus_sprint02 | DEV-26025 | Charge Capture Patient List Management | 7.4.0 | Verified | Closed | Suhani Aneja | Swati Narang
13 | 2 | impetus_sprint02 | DEV-25364 | Physician Portal | 7.4.0 | Verified | Closed | Kumar Saurabh | Swati Narang
14 | 2 | impetus_sprint02 | DEV-24670 | Charge Capture | 7.4.0 | Verified | Closed | Abhishek Kumar | Nitin Anand
15 | 2 | impetus_sprint02 | DEV-24612 | Patient/Visit Merging | 7.4.x FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand
16 | 2 | impetus_sprint02 | DEV-21504 | Charge Capture | 7.4.0 | Verified | Closed | Kumar Saurabh | Swati Narang
17 | 2 | impetus_sprint02 | DEV-18078 | Admin Tools | 7.4.0 | Verified | Closed | Praveen Kumar | Nitin Anand
18 | 2 | impetus_sprint02 | DEV-17715 | Charge Capture | 7.4.0 | Verified | Closed | Praveen Kumar | Nitin Anand
19 | 2 | impetus_sprint02 | DEV-15108 | Admin Tools | 7.4.0 | Verified | Closed | Suhani Aneja | Nitin Anand
20 | 2 | impetus_sprint02 | DEV-11985 | Charge Capture | 7.4.0 | Verified | Closed | Sameer Panda | Nitin Anand
21 | 2 | impetus_sprint02 | DEV-11119 | Charge Capture | 7.4.0 | Not Reproducible | Closed | Praveen Kumar | Swati Narang
22 | 2 | impetus_sprint02 | DEV-10948 | Charge Capture | 7.4.0 | Verified | Closed | Sameer Panda | Swati Narang
1 | 3 | impetus_sprint03 | DEV-33040 | Admin Tools | 7.4.1 | Verified | Closed | Praveen Kumar | Nitin Anand
2 | 3 | impetus_sprint03 | DEV-33013 | Charge Capture | 7.4.0 | Verified | Closed | Kumar Saurabh | Swati Narang
3 | 3 | impetus_sprint03 | DEV-32930 | Charge Capture | 7.4.0 | Verified | Closed | Suhani Aneja | Nitin Anand
4 | 3 | impetus_sprint03 | DEV-32852 | Patient List | 7.4.0 | Verified | Closed | Praveen Kumar | Swati Narang
5 | 3 | impetus_sprint03 | DEV-32830 | Patient List | 7.4.1 | Verified | Closed | Praveen Kumar | Swati Narang
6 | 3 | impetus_sprint03 | DEV-32562 | Manual Registration | 7.4.1 | Verified | Final Review | Abhishek Kumar | Nitin Anand
7 | 3 | impetus_sprint03 | DEV-31967 | Charge Capture | 7.4.1 | Verified | Final Review | Sameer Panda | Nitin Anand
8 | 3 | impetus_sprint03 | DEV-31959 | Physician Portal | 7.4.1 | Verified | Closed | Praveen Kumar | Swati Narang
9 | 3 | impetus_sprint03 | DEV-31389 | Patient List | 5.3.2 | Not Reproducible | Closed | Praveen Kumar | Swati Narang
10 | 3 | impetus_sprint03 | DEV-31035 | Charge Capture | 7.4.1 | Verified | Closed | Abhishek Kumar | Swati Narang
11 | 3 | impetus_sprint03 | DEV-30750 | Dispatcher Meditech MIM Bridge PP | 7.4.2 | Verified | Final Review | Kumar Saurabh | Swati Narang
12 | 3 | impetus_sprint03 | DEV-29587 | Patient List | 7.4.0 | Not Reproducible | Closed | Praveen Kumar
13 | 3 | impetus_sprint03 | DEV-28516 | Charge Capture Physician Portal | 7.4.x FFD | Verified | Final Review | Kumar Saurabh | Swati Narang
14 | 3 | impetus_sprint03 | DEV-24875 | Charge Capture | Declined Issues | Declined | Closed | Abhishek Kumar
15 | 3 | impetus_sprint03 | DEV-24835 | Schedule | 7.4.x FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand
16 | 3 | impetus_sprint03 | DEV-22316 | System/Mobilizer | 7.4.1 | Verified | Closed | Suhani Aneja | Nitin Anand
17 | 3 | impetus_sprint03 | DEV-20942 | Charge Capture | 7.4.x FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand
18 | 3 | impetus_sprint03 | DEV-17145 | Patient List Management | 7.4.1 | Verified | Closed | Suhani Aneja | Swati Narang
19 | 3 | impetus_sprint03 | DEV-15472 | Physician Portal | 7.4.x FFD | Declined | Nothing to Fix | Kumar Saurabh
20 | 3 | impetus_sprint03 | DEV-14763 | Patient List | 7.4.1 | Not Reproducible | Closed | Sameer Panda
21 | 3 | impetus_sprint03 | DEV-14600 | Problem List | 7.4.1 | Not Reproducible | Closed | Abhishek Kumar | Nitin Anand
22 | 3 | impetus_sprint03 | DEV-13403 | Charge Capture | 7.4.1 | Verified | Final Review | Suhani Aneja | Nitin Anand
23 | 3 | impetus_sprint03 | DEV-13222 | Physician Portal | 7.4.1 | Verified | Closed | Kumar Saurabh | Swati Narang
24 | 3 | impetus_sprint03 | DEV-12198 | Patient List | 7.4.1 | Not Reproducible | Closed | Kumar Saurabh | Nitin Anand
25 | 3 | impetus_sprint03 | DEV-11249 | Charge Capture Code Edits | 7.4.1 | Verified | Final Review | Sameer Panda | Nitin Anand
26 | 3 | impetus_sprint03 | DEV-10821 | Patient List | 7.4.1 | Verified | Final Review | Suhani Aneja | Nitin Anand
1 | 4 | impetus_sprint04 | DEV-33522 | Admin Tools | 7.4.x FFD | Verified | Closed | Suhani Aneja | Nitin Anand
2 | 4 | impetus_sprint04 | DEV-33505 | Charge Capture | 7.4.1 | Not Reproducible | Closed |  | Nitin Anand
3 | 4 | impetus_sprint04 | DEV-33372 | Charge Capture | 7.4.x FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand
4 | 4 | impetus_sprint04 | DEV-33197 | Admin Tools | 7.4.x FFD | Verified | Final Review | Praveen Kumar | Swati Narang
5 | 4 | impetus_sprint04 | DEV-33049 | Patient List | 7.4.x FFD | Verified | Final Review | Suhani Aneja | Nitin Anand
6 | 4 | impetus_sprint04 | DEV-32910 | Charge Capture | 7.4.x FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand
7 | 4 | impetus_sprint04 | DEV-31318 | Admin Tools | 7.4.1 | Verified | Closed | Praveen Kumar | Swati Narang
8 | 4 | impetus_sprint04 | DEV-30563 | Admin Tools | 7.4.x FFD | Verified | Final Review | Praveen Kumar | Swati Narang
9 | 4 | impetus_sprint04 | DEV-29833 | Admin Tools | 7.4.x FFD | Not Reproducible | Closed | Praveen Kumar | Swati Narang
10 | 4 | impetus_sprint04 | DEV-29586 | Admin Tools | 7.4.2 | Verified | Final Review | Praveen Kumar | Swati Narang
11 | 4 | impetus_sprint04 | DEV-29396 | Admin Tools | 7.4.x FFD | Declined | Closed | Kumar Saurabh
12 | 4 | impetus_sprint04 | DEV-28990 | Admin Tools | 7.4.x FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand
13 | 4 | impetus_sprint04 | DEV-28194 | Patient List Management | 7.4.1 | Verified | Final Review | Praveen Kumar | Swati Narang
14 | 4 | impetus_sprint04 | DEV-27158 | Admin Tools | 7.4.2 | Verified | Final Review | Kumar Saurabh | Swati Narang
15 | 4 | impetus_sprint04 | DEV-26420 | Admin Tools | 7.4.x FFD | Verified | Final Review | Kumar Saurabh | Nitin Anand
16 | 4 | impetus_sprint04 | DEV-25271 | Patient List | 7.4.1 | Verified | Closed | Suhani Aneja | Swati Narang
17 | 4 | impetus_sprint02 impetus_sprint04 | DEV-24612 | Patient/Visit Merging | 7.4.x FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand
18 | 4 | impetus_sprint04 | DEV-23692 | Charge Capture | 7.4.x FFD | Verified | Closed | Abhishek Kumar | Nitin Anand
19 | 4 | impetus_sprint04 | DEV-22059 | Charge Capture NoteWriter | 7.4.x FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand
20 | 4 | impetus_sprint04 | DEV-13162 | Admin Tools Charge Capture | 7.4.x FFD | Verified | Final Review | Kumar Saurabh | Swati Narang
21 | 4 | impetus_sprint04 | DEV-12493 | Admin Tools Patient List | 7.4.x FFD | Verified | Final Review | Suhani Aneja | Nitin Anand
22 | 4 | impetus_sprint04 | DEV-12038 | Admin Tools | 7.4.x FFD | Verified | Final Review | Sameer Panda | Nitin Anand
23 | 4 | impetus_sprint04 | DEV-11034 | Admin Tools | 7.4.x FFD | Verified | Final Review | Suhani Aneja | Nitin Anand
24 | 4 | impetus_sprint04 | DEV-10493 | Admin Tools Charge Capture | 7.4.x FFD | Verified | Final Review | Sameer Panda | Nitin Anand
25 | 4 | impetus_sprint04 | DEV-10339 | Admin Tools Patient List | 7.4.x FFD | Not Reproducible | Final Review | Sameer Panda | Nitin Anand
1 | 5 | impetus_sprint05 | DEV-33953 | Admin Tools | 7.4.2 | Verified | Final Review | Suhani Aneja | Nitin Anand
2 | 5 | impetus_sprint05 | DEV-33811 | Patient List Management | 7.4.2 | Verified | Final Review | Suhani Aneja
3 | 5 | impetus_sprint05 | DEV-33606 | Patient List | 7.4.x FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand
4 | 5 | impetus_sprint05 | DEV-33195 | Admin Tools | 7.4.x FFD | Verified | Final Review | Praveen Kumar | Swati Narang
5 | 5 | impetus_sprint05 | DEV-30571 | Desktop Clinical Results | 7.4.2 | Verified | Final Review | Abhishek Kumar | Nitin Anand
6 | 5 | impetus_sprint05 | DEV-30278 | Desktop Clinical Results | 7.4.2 | Verified | Final Review | Abhishek Kumar | Nitin Anand
7 | 5 | impetus_sprint05 | DEV-28276 | Physician Portal | 7.4.2 | Verified | Final Review | Kumar Saurabh | Swati Narang
8 | 5 | impetus_sprint05 | DEV-28091 | Charge Capture | 7.4.2 | Not Reproducible | Final Review | Praveen Kumar | Swati Narang
9 | 5 | impetus_sprint05 | DEV-23216 | Admin Tools | 7.4.2 | Verified | Final Review | Kumar Saurabh | Swati Narang
10 | 5 | impetus_sprint05 | DEV-22331 | Meditech MIM Bridge Physician Portal | 7.4.x FFD | Verified | Final Review | Kumar Saurabh | Swati Narang
1 | 6 | impetus_sprint06 | DEV-33328 | Charge Capture | 7.4.2 | Verified | Final Review | Kumar Saurabh | Swati Narang |  | sprint05 |  | Medium
2 | 6 | impetus_sprint06 | DEV-31000 | Admin Tools Charge | 7.4.2 | Verified | Final Review | Kumar Saurabh | Swati Narang |  | sprint05 |  | Medium
3 | 6 | impetus_sprint06 | DEV-30838 | Charge Capture | 7.4.2 | Not Reproducible | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | Medium
4 | 6 | impetus_sprint06 | DEV-30777 | Charge Capture | 7.4.2 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | Medium
5 | 6 | impetus_sprint06 | DEV-30653 | Desktop Clinical Results | 7.4.2 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | Medium
6 | 6 | impetus_sprint06 | DEV-28028 | Charge Capture | 7.4.2 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | Medium
7 | 6 | impetus_sprint06 | DEV-27747 | Charge Capture | 7.4.2 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | Medium
8 | 6 | impetus_sprint06 | DEV-27355 | Desktop Clinical Results | 7.4.2 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  | sprint05 |  | High
9 | 6 | impetus_sprint06 | DEV-25071 | Charge Capture | 7.4.2 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | Medium
10 | 6 | impetus_sprint06 | DEV-24089 | Admin Tools Charge Capture | 7.4.2 | Declined | Final Review | Kumar Saurabh |  |  | sprint04 | Missing Jira Information
11 | 6 | impetus_sprint06 | DEV-23841 | Admin Tools | 7.4.2 | Verified | Final Review | Kumar Saurabh | Swati Narang |  | sprint04 | More Complex
12 | 6 | impetus_sprint06 | DEV-22188 | Charge Capture | 7.4.2 | Not Reproducible | Final Review | Sameer Panda | Nitin Anand
13 | 6 | impetus_sprint06 | DEV-21455 | System/Mobilizer | 7.4.2 | Verified | Final Review | Sameer Panda | Nitin Anand |  | sprint05
14 | 6 | impetus_sprint06 | DEV-19669 | Charge Capture | 7.4.2 | Working as Designed | Final Review | Sameer Panda
15 | 6 | impetus_sprint06 | DEV-15655 | Admin Tools | 7.4.2 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | Low
16 | 6 | impetus_sprint06 | DEV-13747 | Admin Tools | 7.4.2 | Verified | Final Review | Sameer Panda | Nitin Anand |  |  |  | Low
17 | 6 | impetus_sprint06 | DEV-10816 | Manual Registration | 7.4.2 | Verified | Final Review | Suhani Aneja | Nitin Anand |  | sprint05 |  | Low
1 | 7 | impetus_sprint07 | DEV-34644 | Upgrades | 7.4.2 | Verified | Closed | Sameer Panda |  | Jon Piro Tested
2 | 7 | impetus_sprint07 | DEV-34556 | Physician Portal | 7.4.2 | Verified | Final Review | Sameer Panda |  | Dan Binder tested
3 | 7 | impetus_sprint07 | DEV-34328 | Charge Capture | 7.4.2 | Verified | Final Review | Suhani Aneja | Nitin Anand
4 | 7 | impetus_sprint07 | DEV-33071 | System/Mobilizer | 7.4.2 | Verified | Final Review | Suhani Aneja | Nitin Anand
5 | 7 | impetus_sprint07 | DEV-32249 | Physician Portal | 7.4.2 | Verified | Final Review | Suhani Aneja | Nitin Anand |  | sprint06 | For Review
6 | 7 | impetus_sprint07 | DEV-31680 | Admin Tools Architecture Code Edits | 7.4.2 | Verified | Final Review | Praveen Kumar | Swati Narang
7 | 7 | impetus_sprint07 | DEV-30505 | Charge Capture | 7.4.2 | Verified | Final Review | Kumar Saurabh | Swati Narang |  | sprint06 | Revisit
8 | 7 | impetus_sprint07 | DEV-29525 | Charge Capture | 7.4.2 | Verified | Final Review | Praveen Kumar | Swati Narang
9 | 7 | impetus_sprint07 | DEV-29320 | Messaging | 7.4.2 | Verified | Final Review | Suhani Aneja | Nitin Anand |  | sprint06 | Did Not Work
10 | 7 | impetus_sprint07 | DEV-28091 | Charge Capture | 7.4.2 | Not Reproducible | Final Review | Kumar Saurabh | Swati Narang
11 | 7 | impetus_sprint07 | DEV-24719 | Admin Tools Handheld (Old Palm/WM) | 7.4.2 | Verified | Final Review | Sameer Panda | Nitin Anand
12 | 7 | impetus_sprint07 | DEV-23200 | Charge Capture | 7.4.2 | Verified | Final Review | Praveen Kumar | Swati Narang
13 | 7 | impetus_sprint07 | DEV-21641 | Forms | 7.4.2 | Verified | Final Review | Praveen Kumar | Swati Narang |  | sprint01 | Revisit
14 | 7 | impetus_sprint07 | DEV-13499 | System/Mobilizer | 7.4.2 | Not Reproducible | Final Review | Kumar Saurabh
15 | 7 | portal_facelift_impetus | DEV-34435 | Physician Portal | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
16 | 7 | portal_facelift_impetus | DEV-34434 | Physician Portal | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
17 | 7 | portal_facelift_impetus | DEV-34433 | Physician Portal | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
18 | 7 | portal_facelift_impetus | DEV-34432 | Physician Portal | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
19 | 7 | portal_facelift_impetus | DEV-34431 | Physician Portal | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
20 | 7 | portal_facelift_impetus | DEV-34430 | Physician Portal | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
21 | 7 | portal_facelift_impetus | DEV-34428 | Physician Portal | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
22 | 7 | portal_facelift_impetus | DEV-34426 | Physician Portal Problem List | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
23 | 7 | portal_facelift_impetus | DEV-34425 | Physician Portal Problem List | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
24 | 7 | portal_facelift_impetus | DEV-34424 | Physician Portal Problem List | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
25 | 7 | portal_facelift_impetus | DEV-34423 | Physician Portal | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
26 | 7 | portal_facelift_impetus | DEV-34422 | NoteWriter Physician Portal | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
27 | 7 | portal_facelift_impetus | DEV-34420 | Physician Portal | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
28 | 7 | portal_facelift_impetus | DEV-34419 | Physician Portal | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
29 | 7 | portal_facelift_impetus | DEV-34415 | Physician Portal | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
30 | 7 | portal_facelift_impetus | DEV-34414 | Physician Portal | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
31 | 7 | portal_facelift_impetus | DEV-34413 | Physician Portal | 7.6.0, HIMSS 2012 | Verified | Closed | Abhishek Kumar | Nitin Anand | Part of Sprint07
1 | 8 | impetus_sprint08 | DEV-34648 | Charge Capture | 7.5.2 | Verified | Final Review | Kumar Saurabh | Swati Narang
2 | 8 | impetus_sprint08 | DEV-34351 | Admin Tools | 7.4.2 | Verified | Closed | Sameer Panda | Nitin Anand
3 | 8 | impetus_sprint08 | DEV-33356 | Charge Capture | 7.5.2 | Verified | Final Review | Suhani Aneja | Nitin Anand
4 | 8 | impetus_sprint08 | DEV-30811 | Admin Tools | 7.5.2 | Not Reproducible | Final Review | Sameer Panda | Nitin Anand
5 | 8 | impetus_sprint08 | DEV-30589 | Charge Capture | 7.5.2 | Verified | Final Review | Kumar Saurabh | Swati Narang
6 | 8 | impetus_sprint08 | DEV-30265 | Charge Capture | 7.5.2 | Duplicate | Final Review | Abhishek Kumar | Nitin Anand
7 | 8 | impetus_sprint08 | DEV-27846 | Admin Tools, Charge Capture | 7.5.2 | Not Reproducible | Final Review | Praveen Kumar | Swati Narang
8 | 8 | impetus_sprint08 | DEV-27749 | Charge Capture | 7.5.2 | Verified | Final Review | Praveen Kumar | Swati Narang
9 | 8 | impetus_sprint08 | DEV-27746 | Charge Capture | 7.4.2 | Verified | Final Review | Praveen Kumar | Swati Narang |  | sprint07 | More Complex
10 | 8 | impetus_sprint08 | DEV-26624 | Charge Capture | 7.5.2 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  | sprint07 | Did Not Work
11 | 8 | impetus_sprint08 | DEV-25568 | Charge Capture | 7.5.2 | Verified | Final Review | Kumar Saurabh | Swati Narang
12 | 8 | impetus_sprint08 | DEV-25120 | Admin Tools | 7.5.2 | Verified | Final Review | Suhani Aneja
13 | 8 | impetus_sprint08 | DEV-24835 | Schedule | 7.5.2 | Verified | Final Review | Abhishek Kumar | Nitin Anand
14 | 8 | impetus_sprint08 | DEV-20985 | Charge Capture | 7.5.2 | Declined | Closed | Kumar Saurabh
15 | 8 | impetus_sprint08 | DEV-19968 | Charge Capture | 7.5.2 | Obsolete | Closed | Kumar Saurabh | Swati Narang
16 | 8 | impetus_sprint08 | DEV-19026 | Admin Tools, System/Mobilizer | 7.5.2 | Not Reproducible | Final Review | Suhani Aneja | Nitin Anand
17 | 8 | impetus_sprint08 | DEV-18564 | Charge Capture | 7.5.2 | Verified | Final Review | Praveen Kumar | Swati Narang
18 | 8 | impetus_sprint08 | DEV-17935 | Charge Capture | 7.5.2 | Verified | Final Review | Sameer Panda | Nitin Anand
19 | 8 | impetus_sprint08 | DEV-16475 | Charge Capture | 7.5.2 | Verified | Final Review | Praveen Kumar | Swati Narang
20 | 8 | impetus_sprint08 | DEV-14178 | Charge Capture | 7.5.2 | Verified | Final Review | Kumar Saurabh | Swati Narang
21 | 8 | impetus_sprint08 | DEV-13391 | Admin Tools, Charge Capture | 7.5.2 | Verified | Final Review | Suhani Aneja | Nitin Anand
22 | 8 | impetus_sprint08 | DEV-10446 | Charge Capture | 7.5.2 | Verified | Final Review | Sameer Panda | Nitin Anand
1 | 9 | impetus_sprint09 | DEV-35023 | Patient List | 7.4.2 | Verified | Final Review | Praveen Kumar | Nitin Anand
2 | 9 | impetus_sprint09 | DEV-34963 | Charge Capture | 7.5.2 | Verified | Final Review | Abhishek Kumar | Nitin Anand
3 | 9 | impetus_sprint09 | DEV-28532 | Charge Capture | 7.5.2 | Verified | Final Review | Suhani Aneja | Nitin Anand
4 | 9 | impetus_sprint09 | DEV-23769 | Charge Capture | 7.5.2 | Not Reproducible | Final Review | Praveen Kumar | Nitin Anand
5 | 9 | impetus_sprint09 | DEV-22749 | Charge Capture | 7.5.2 | Obsolete | Nothing to Fix | Praveen Kumar | Nitin Anand
6 | 9 | impetus_sprint09 | DEV-22623 | Charge Capture | 7.5.2 | Verified Internally | Final Review | Suhani Aneja | Nitin Anand
7 | 9 | impetus_sprint09 | DEV-20123 | Charge Capture | 7.5.2 | Working as Designed | Final Review | Kumar Saurabh | Nitin Anand
8 | 9 | impetus_sprint09 | DEV-17950 | Charge Capture | 7.5.2 | Not Reproducible | Final Review | Sameer Panda | Nitin Anand
9 | 9 | impetus_sprint09 | DEV-16353 | Charge Capture | 7.5.2 | Working as Designed | Final Review | Kumar Saurabh | Swati Narang
10 | 9 | impetus_sprint09 | DEV-11208 | Admin Tools | Future - to be scheduled | Not Reproducible | Final Review | Sameer Panda | Nitin Anand
11 | 9 | impetus_sprint09 | DEV-10825 | Patient List Management | 7.5.2 | Working as Designed | Final Review | Suhani Aneja | Nitin Anand
12 | 9 | impetus_sprint09 | DEV-10694 | Admin Tools | 7.5.2 | Verified | Final Review | Sameer Panda | Nitin Anand
13 | 9 | impetus_sprint09 | DEV-10588 | Admin Tools, Charge Capture | 7.5.2 | Not Reproducible | Final Review | Kumar Saurabh | Swati Narang
14 | 9 | impetus_sprint09 | DEV-9323 | Admin Tools | 7.5.2 | Obsolete | Final Review | Sameer Panda | Nitin Anand
1 | 10 | impetus_sprint10 | DEV-35159 | Admin Tools | 7.5.2 | Verified | Final Review | Sameer Panda | Swati Narang
2 | 10 | impetus_sprint10 | DEV-35114 | Charge Capture | 7.5.2 | Verified | Final Review | Suhani Aneja | Nitin Anand
3 | 10 | impetus_sprint10 | DEV-34587 | Physician Portal | 7.5.2 | Verified | Final Review | Suhani Aneja | Nitin Anand
4 | 10 | impetus_sprint10 | DEV-34135 | Provider Directory | 7.5.2 | Verified | Final Review | Kumar Saurabh | Swati Narang
5 | 10 | impetus_sprint10 | DEV-33663 | Physician Portal | 7.5.2 | Verified | Final Review | Sameer Panda | Nitin Anand
6 | 10 | impetus_sprint10 | DEV-32607 | Charge Capture | 7.5.2 | Verified | Final Review | Kumar Saurabh | Swati Narang
7 | 10 | impetus_sprint10 | DEV-27257 | Charge Capture | 7.5.2 | Verified | Final Review | Suhani Aneja | Nitin Anand
8 | 10 | impetus_sprint10 | DEV-20941 | Charge Capture | Declined Issues | Declined | Closed | Abhishek Kumar | Nitin Anand
9 | 10 | impetus_sprint10 | DEV-20386 | Admin Tools, Charge Capture | 7.5.2 | Verified | Final Review | Sameer Panda | Swati Narang
10 | 10 | impetus_sprint10 | DEV-15874 | Admin Tools | 7.5.2 | Verified Internally | Closed | Suhani Aneja | Swati Narang
11 | 10 | impetus_sprint10 | DEV-10824 | Admin Tools | 7.5.2 | Verified | Final Review | Kumar Saurabh | Swati Narang
12 | 10 | impetus_sprint10 | DEV-10719 | Desktop Clinical Results, Dispatcher | 7.5.2 | Verified | Final Review | Abhishek Kumar | Nitin Anand
1 | 11 | impetus_sprint11 | DEV-35294 | Admin Tools, Charge Capture | 7.5.2 | Verified | Final Review | Sameer Panda | Nitin Anand
2 | 11 | Partners, impetus_sprint11 | DEV-35253 | Charge Capture | 7.5.2 | Duplicate | Nothing to Fix | Suhani Aneja
3 | 11 | impetus_sprint11 | DEV-35201 | NoteWriter | 7.5.2 | Verified | Final Review | Sameer Panda | Nitin Anand
4 | 11 | impetus_sprint11 | DEV-34970 | Patient List | 7.5.2 | Verified | Final Review | Suhani Aneja | Swati Narang
5 | 11 | impetus_sprint11 | DEV-34921 | Admin Tools | 7.5.2 | Verified | Final Review | Sameer Panda | Swati Narang
6 | 11 | impetus_sprint11 | DEV-33661 | Desktop Clinical Results | 7.5.2 | Verified | Final Review | Sameer Panda | Swati Narang
7 | 11 | impetus_sprint11 | DEV-33617 | Charge Analytics | 7.5.2 | Verified | Final Review | Suhani Aneja | Swati Narang
8 | 11 | impetus_sprint11 | DEV-20489 | Charge Capture | 7.5.2 | Verified | Final Review | Suhani Aneja | Nitin Anand
9 | 11 | impetus_sprint11 | DEV-11036 | Admin Tools, Charge Capture | 7.5.2 | Verified | Final Review | Suhani Aneja | Nitin Anand
10 | 11 | impetus_sprint11 | DEV-9308 | Charge Capture | 7.5.2 | Verified | Final Review | Abhishek Kumar | Nitin Anand
1 | 12 | impetus_sprint12 | DEV-35441 | Admin Tools | 7.5.3 | Verified | Final Review | Sameer Panda | Swati Narang |  |  |  | Low |  | Low | 1 | 1
2 | 12 | impetus_sprint12 | DEV-35434 | Admin Tools | 7.5.2 | Duplicate | Final Review | Suhani Aneja | Nitin Anand |  |  |  | Low |  | Low | 1 | 1
3 | 12 | impetus_sprint12 | DEV-34926 | System/Mobilizer | 7.5.3 | Verified | Final Review | Kumar Saurabh |  |  |  |  | Very High |  |  | 3 to 5
4 | 12 | Partners, ambulatory, impetus_sprint12 | DEV-34755 | Charge Capture, Handheld (TotalCross), iPhone | 7.5.2 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | Medium |  |  | 3 to 5 | 3
5 | 12 | impetus_sprint12 | DEV-30272 | Desktop Clinical Results | 7.5.3 | Unresolved | Final Review | Kumar Saurabh | Swati Narang |  | sprint09 | More Complex | Very High |  | Very High | 5 | 5
6 | 12 | impetus_sprint12 | DEV-24687 | Admin Tools | 7.5.3 | Verified | Final Review | Sameer Panda | Nitin Anand |  |  |  | Low |  | Low | 1 | 1
7 | 12 | HCA_6Admin, impetus_sprint12 | DEV-23033 | Meditech MIM Bridge | 7.5.3 | Verified | Final Review | Kumar Saurabh | Nitin Anand |  |  |  | High |  |  | 3 to 5
8 | 12 | impetus_sprint12 | DEV-20920 | Charge Capture | 7.5.3 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | Medium |  | Medium | 1 to 3 | 3
9 | 12 | impetus_sprint12 | DEV-19006 | Admin Tools, Architecture | 7.5.2 | Verified | Final Review | Praveen Kumar | Swati Narang |  | sprint09 | More Complex | Very High |  |  | 20 to 25 | 30
10 | 12 | impetus_sprint12 | DEV-18442 | Dispatcher, Physician Portal | Declined Issues | Workaround Provided | Closed | Sameer Panda |  |  |  |  | Low |  | Low | 1 | 1
11 | 12 | impetus_sprint12 | DEV-12375 | Handheld (TotalCross), iPhone, Light Browser, Physician Portal | 7.5.3 | Verified | Final Review | Suhani Aneja | Swati Narang |  | sprint10 | Scope Creep | High |  |  | 3 to 4
12 | 12 | impetus_sprint12 | DEV-9233 | Admin Tools | 7.5.3 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | Medium |  |  | 3
13 | 12 | impetus_sprint12 | DEV-8789 | Desktop Clinical Results | Declined Issues | Obsolete | Closed | Sameer Panda |  |  |  |  | Medium |  | Low | 2 | 1
1 | 13 | impetus_sprint13 | DEV-35677 | Charge Capture | 7.5.3 | Not Reproducible | Final Review | Sameer Panda | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
2 | 13 | impetus_sprint13 | DEV-35553 | Admin Tools | 7.5.3 | Verified | Final Review | Kumar Saurabh | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 3
3 | 13 | impetus_sprint13 | DEV-35229 | System/Mobilizer | 7.5.3 | Verified | Final Review | Sameer Panda |  | Jon Piro Tested |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
4 | 13 | impetus_sprint13 | DEV-34993 | Charge Capture | 7.5.3 | Not Reproducible | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
5 | 13 | impetus_sprint13 | DEV-34777 | Admin Tools | 7.5.3 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
6 | 13 | HL7, impetus_sprint13 | DEV-34566 | Admin Tools | 7.5.3 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
7 | 13 | impetus_sprint13 | DEV-28791 | Admin Tools | 7.5.3 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 1 | 1
8 | 13 | impetus_sprint13 | DEV-27525 | Charge Capture | 7.5.3 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
9 | 13 | impetus_sprint13 | DEV-25486 | Admin Tools, System/Mobilizer | 7.5.3 | Verified | Final Review | Sameer Panda | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
10 | 13 | impetus_sprint13 | DEV-24431 | Charge Capture | 7.5.3 | Duplicate | Nothing to Fix | Suhani Aneja |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
11 | 13 | impetus_sprint13 | DEV-24077 | Handheld (TotalCross), iPhone, Light Browser, Physician Portal | 7.5.3 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
12 | 13 | impetus_sprint13 | DEV-21237 | Admin Tools | 7.5.3 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 2 | 2 | 2 | 3 | 4
13 | 13 | impetus_sprint13 | DEV-14565 | Admin Tools | 7.5.3 | Obsolete | Nothing to Fix | Sameer Panda |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
14 | 13 | impetus_sprint13 | DEV-13248 | Charge Capture | 7.5.3 | Obsolete | Final Review | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
15 | 13 | impetus_sprint13 | DEV-11480 | Charge Capture | 7.5.3 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
16 | 13 | impetus_sprint13 | DEV-11313 | Charge Capture | 7.5.3 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 2 | 2 | 2 | 3 | 3
17 | 13 | impetus_sprint13 | DEV-9821 | Admin Tools, Performance | 7.5.3 | Verified | Final Review | Sameer Panda | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
1 | 14 | impetus_sprint14 | DEV-35597 | NoteWriter | 7.6.0 | Verified | Final Review | Sameer Panda | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
2 | 14 | impetus_sprint14 | DEV-35420 | Dispatcher | 7.x-MaintenanceTriage | Working as Designed | Nothing to Fix | Sameer Panda |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
3 | 14 | impetus_sprint14 | DEV-35382 | Charge Capture | 7.6.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
4 | 14 | Portal_Facelift, impetus_Sprint14 | DEV-34436 | Physician Portal | 7.6.0 | Verified | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
5 | 14 | Portal_Facelift, impetus_Sprint14 | DEV-34429 | Physician Portal | 7.6.0 | Verified | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
6 | 14 | impetus_sprint14 | DEV-34400 | Admin Tools | 7.6.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
7 | 14 | impetus_sprint14 | DEV-30305 | Charge Capture | 7.6.0 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 2 | 2 | 1 | 3 | 2
8 | 14 | impetus_sprint14 | DEV-28091 | Charge Capture | 7.6.0 | Not Reproducible | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
9 | 14 | impetus_sprint14 | DEV-26251 | Charge Capture | 7.6.0 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
10 | 14 | impetus_sprint14 | DEV-24919 | Admin Tools | 7.6.0 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
11 | 14 | impetus_sprint14 | DEV-24669 | Admin Tools | 7.6.0 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 2 | 2 | 2 | 4 | 4
12 | 14 | impetus_sprint14 | DEV-20444 | Charge Capture | 7.6.0 | Verified | Closed | Praveen Kumar | Swati Narang |  |  |  | 2 | 2 | 2 | 3 | 3
13 | 14 | impetus_Sprint14 | DEV-20124 | Charge Capture | MinorEnhancementTriage | Duplicate | Nothing to Fix | Praveen Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
14 | 14 | impetus_sprint14 | DEV-18308 | Charge Capture | 7.6.0 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 2 | 2 | 1 | 3 | 2
15 | 14 | impetus_Sprint14 | DEV-18040 | Charge Capture | 7.6.0 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
16 | 14 | impetus_Sprint14 | DEV-16812 | Custom Visit Types | 7.6.0 | Verified | Final Review | Sameer Panda | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
17 | 14 | impetus_sprint14 | DEV-16129 | Charge Capture | 7.5.3 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 2 | 3 | 2 | 3 | 3
18 | 14 | impetus_sprint14 | DEV-14559 | Admin Tools | 7.6.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 2 | 2 | 2 | 4 | 3
19 | 14 | impetus_sprint14 | DEV-13135 | Messaging | 7.6.0 | Obsolete | Nothing to Fix | Suhani Aneja |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
20 | 14 | impetus_sprint14 | DEV-9925 | Charge Capture | 7.6.0 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 2 | 3 | 3 | 2 | 2
1 | 15 | Partners, impetus_sprint15 | DEV-35386 | Admin Tools | 7.6.0 | Verified | Closed | Kumar Saurabh | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
2 | 15 | impetus_sprint15 | DEV-35329 | Charge Capture | 7.6.0 | Verified | Closed | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 1.5
3 | 15 | impetus_sprint15 | DEV-27944 | Sign-Out | 7.6.0 | Not Reproducible | Closed | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
4 | 15 | HCA_6Admin, impetus_sprint15 | DEV-23466 | Admin Tools | 7.6.0 | Verified | Closed | Kumar Saurabh | Swati Narang |  |  |  | 2 | 2 | 1 | 3 | 2
5 | 15 | impetus_sprint15 | DEV-21198 | Desktop Clinical Results | 7.6.0 | Not Reproducible | Closed | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
6 | 15 | impetus_sprint15 | DEV-19394 | Charge Capture | 7.6.0 | Verified | Closed | Kumar Saurabh | Swati Narang |  |  |  | 2 | 2 | 3 | 4 | 12
7 | 15 | impetus_sprint15 | DEV-14311 | Messaging | 7.6.0 | Verified | Closed | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 1.5
8 | 15 | impetus_sprint15 | DEV-12908 | Charge Capture | 7.6.0 | Verified | Closed | Suhani Aneja | Nitin Anand |  |  |  | 2 | 2 | 2 | 3 | 3
9 | 15 | impetus_sprint15 | DEV-11673 | Desktop Clinical Results | 7.6.0 | Verified | Closed | Kumar Saurabh | Swati Narang |  |  |  | 2 | 2 | 2 | 3 | 3
10 | 15 | impetus_sprint15 | DEV-9313 | Provider Directory | 7.6.0 | Verified | Closed | Praveen Kumar | Swati Narang |  |  |  | 2 | 2 | 2 | 3 | 3
11 | 15 | impetus_sprint15 | DEV-9146 | Patient List Management | 7.6.0 | Verified | Closed | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
12 | 15 | Portal_Facelift | DEV-35997 | Admin Tools | 7.6.0 | Not Reproducible | Closed | Kumar Saurabh | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
13 | 15 | Portal_Facelift | DEV-35996 | Physician Portal | 7.6.0 | Verified | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
14 | 15 | Portal_Facelift | DEV-35897 | Provider Directory | 7.6.0 | Not Reproducible | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
15 | 15 | Portal_Facelift | DEV-35877 | Patient List | 7.6.0 | Verified | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
16 | 15 | Portal_Facelift | DEV-35862 | Provider Directory | 7.6.0 | Verified | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 2 | 2 | 2 | 3 | 3
17 | 15 | Portal_Facelift | DEV-35855 | Admin Tools | 7.6.0 | Verified | Closed | Praveen Kumar | Swati Narang |  |  |  | 1 | 2 | 1 | 2 | 2
18 | 15 | portal_facelift | DEV-35827 | Physician Portal | 7.6.0 | Verified | Closed | Kumar Saurabh | Swati Narang |  |  |  | 1 |  | 0.8 | 2 | 1
19 | 15 | Portal_Facelift | DEV-35787 | Manual Registration, Physician Portal | 7.6.0 | Verified | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
20 | 15 | Portal_Facelift | DEV-35753 | Physician Portal | 7.6.0 | Not Reproducible | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
21 | 15 | Portal_Facelift | DEV-35630 | Problem List | 7.6.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
22 | 15 | Portal_Facelift | DEV-35346 | Physician Portal | 7.6.0 | Not Reproducible | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
1 | 16 | impetus_Sprint16 | DEV-36317 | Charge Capture | 7.6.0 | Verified | Closed | Abhishek Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
2 | 16 | impetus_Sprint16 | DEV-35902 | Schedule | 7.6.0 | Verified | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
3 | 16 | impetus_Sprint16 | DEV-35899 | Messaging | 760FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
4 | 16 | impetus_Sprint16 | DEV-35751 | Charge Capture | 7.6.0 | Not Reproducible | Closed | Sameer Panda | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
5 | 16 | impetus_sprint16 | DEV-35728 | Charge Capture | 760FFD | Unresolved | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
6 | 16 | impetus_sprint16 | DEV-35532 | Charge Capture | 760FFD | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
7 | 16 | impetus_sprint16 | DEV-33208 | Auditing | 760FFD | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 2 | 2 | 1 | 3 | 2
8 | 16 | impetus_sprint16 | DEV-30630 | Database | 760FFD | Data Issue | Nothing to Fix | Kumar Saurabh |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
9 | 16 | impetus_sprint16 | DEV-22017 | Physician Portal | 760FFD | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 1
10 | 16 | impetus_sprint16 | DEV-20262 | Charge Capture | 760FFD | Working as Designed | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 0.8 | 2 | 1
11 | 16 | impetus_sprint16 | DEV-13740 | Auditing | 760FFD | Not Reproducible | Final Review | Kumar Saurabh |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
12 | 16 | impetus_Sprint16 | DEV-12168 | Patient List Management | 760FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
13 | 16 | impetus_Sprint16 | DEV-10368 | Admin Tools | 760FFD | Verified | Final Review | Sameer Panda | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
14 | 16 | Portal_Facelift | DEV-36322 | Charge Capture | 7.6.0 | Verified | Closed | Abhishek Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
15 | 16 | Portal_Facelift | DEV-36303 | Admin Tool | 7.6.0 | Verified | Closed | Abhishek Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
16 | 16 | Portal_Facelift | DEV-36262 | Charge Capture, Schedule | 7.6.0 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
17 | 16 | Portal_Facelift | DEV-36252 | Dispatcher | 7.5.3, 7.6.0 | Verified | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
18 | 16 | Portal_Facelift | DEV-36095 | Admin Tool | 7.6.0 | Verified | Closed | Abhishek Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
19 | 16 | Portal_Facelift | DEV-35928 | Patient List | 7.6.0 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
20 | 16 | Portal_Facelift | DEV-35860 | Problem List | 7.6.0 | Unresolved | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
21 | 16 | Portal_Facelift | DEV-35794 | Admin Tools | 7.6.0 | Verified | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
22 | 16 | Portal_Facelift | DEV-35793 | Charge Capture | 7.6.0 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
23 | 16 | Portal_Facelift | DEV-35756 | Desktop Clinical Results | 7.6.0 | Not Reproducible | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 2 | 0.8 | 0.8 | 2 | 1
24 | 16 | Portal_Facelift | DEV-35748 | Physician Portal | 7.6.0 | Verified | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
25 | 16 | Portal_Facelift | DEV-35739 | Charge Capture | 7.6.0 | Verified | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
26 | 16 | Portal_Facelift | DEV-35663 | Physician Portal | 7.6.0 | Verified | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
1 | 17 | impetus_sprint17 | DEV-36507 | Physician Portal | 760FFD | Not Reproducible | Final Review | Sameer Panda | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
2 | 17 | impetus_sprint17 | DEV-36304 | Charge Capture, Schedule | 760FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
3 | 17 | impetus_sprint17 | DEV-35533 | Charge Capture | 760FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
4 | 17 | impetus_sprint17 | DEV-34974 | Admin Tools, CPOE | 760FFD | Verified | Final Review | Sameer Panda | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
5 | 17 | impetus_sprint17 | DEV-32845 | Charge Capture | 760FFD | Duplicate | Final Review | Praveen Kumar | Swati Narang
6 | 17 | impetus_sprint17 | DEV-30659 | Desktop Clinical Results | 760FFD | Verified | Final Review | Abhishek Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
7 | 17 | impetus_sprint17 | DEV-26847 | NoteWriter | 760FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
8 | 17 | HCA_6Admin, impetus_sprint17 | DEV-25131 | Admin Tools | 760FFD | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
9 | 17 | impetus_sprint17 | DEV-24943 | Physician Portal | 760FFD | Verified | Final Review | Suhani Aneja | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
10 | 17 | impetus_sprint17 | DEV-16821 | Admin Tools | Declined Issues | Obsolete | Closed | Kumar Saurabh |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
11 | 17 | impetus_sprint17 | DEV-13667 | Patient List, Patient List Management | 760FFD | Not Reproducible | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 0.8 | 2 | 1
12 | 17 | impetus_sprint17 | DEV-12790 | Provider Directory | 760FFD | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
13 | 17 | impetus_sprint17 | DEV-12058 | System/Mobilizer | 760FFD | Verified | Final Review | Sameer Panda | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
14 | 17 | impetus_sprint17 | DEV-11738 | Admin Tools | 760FFD | Verified | Final Review | Suhani Aneja | Nitin Anand | Was in Review | Sprint 16 |  | 1 | 1 | 1 | 2 | 2
15 | 17 | impetus_sprint17 | DEV-10494 | Desktop Clinical Results | 760FFD | Unresolved | Open | Abhishek Kumar |  |  |  |  | 1 | 1 |  | 2
16 | 17 | impetus_sprint17 | DEV-10331 | Charge Capture | 7.6.0 | Duplicate | Closed | Suhani Aneja |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
17 | 17 | impetus_sprint17 | DEV-10285 | Desktop Clinical Results | 760FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
18 | 17 | impetus_sprint17 | DEV-9571 | eSignature | Future - to be scheduled | Obsolete | Nothing to Fix | Praveen Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
19 | 17 | impetus_sprint17 | DEV-9416 | System/Mobilizer | 760FFD | Not Reproducible | Nothing to Fix | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
20 | 17 | impetus_sprint17 | DEV-9297 | Patient List | Declined Issues | Obsolete | Closed | Kumar Saurabh |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
1 | 18 | impetus_sprint18 | DEV-36343 | Admin Tools | 760FFD | Verified | Final Review | Sameer Panda | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
2 | 18 | impetus_sprint18 | DEV-36228 | Charge Capture | 760FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 2 | 2 | 3
3 | 18 | Partners, impetus_sprint18 | DEV-35252 | Charge Capture | 760FFD | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
4 | 18 | impetus_sprint18 | DEV-35249 | Charge Capture | 760FFD | Not Reproducible | Final Review | Sameer Panda | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
5 | 18 | impetus_sprint18 | DEV-35163 | Charge Capture, Patient List | 760FFD | Verified | Final Review | Suhani Aneja | Swati Narang |  |  |  | 1 |  | 1 | 2 | 2
6 | 18 | impetus_sprint18 | DEV-34855 | Admin Tools | 760FFD | Not Reproducible | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
7 | 18 | impetus_sprint18 | DEV-31486 | Charge Capture | 760FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
8 | 18 | impetus_sprint18 | DEV-31459 | Charge Capture | 760FFD | Not Reproducible | Final Review | Sameer Panda | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
9 | 18 | impetus_sprint18 | DEV-31434 | Desktop Clinical Results | 760FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 2 | 2 | 3
10 | 18 | impetus_sprint18 | DEV-24206 | Charge Capture | 760FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
11 | 18 | impetus_sprint18 | DEV-23755 | Charge Capture | 760FFD | Verified | Final Review | Suhani Aneja | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
12 | 18 | impetus_sprint18 | DEV-22515 | Manual Registration | 760FFD | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
13 | 18 | impetus_sprint18 | DEV-16401 | Charge Capture | 760FFD | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 2 | 2 | 2 | 3 | 3
14 | 18 | impetus_sprint18 | DEV-16359 | Patient List Management | 760FFD | Obsolete | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
15 | 18 | impetus_sprint18 | DEV-15842 | Installation | Future - to be scheduled | Known Issue | Nothing to Fix | Sameer Panda |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
16 | 18 | impetus_sprint18 | DEV-12953 | Charge Capture | 760FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
17 | 18 | impetus_sprint18 | DEV-12583 | Patient List | 760FFD | Obsolete | Final Review | Abhishek Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
1 | 19 | impetus_sprint19 | DEV-36603 | Charge Capture | 7.6.1 | Verified | Final Review | Sameer Panda | Nitin Anand |  |  |  | 1 | 1 | 1 | 1 | 2
2 | 19 | impetus_sprint19, partners | DEV-36134 | Physician Portal | 7.6.1 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
3 | 19 | impetus_sprint19 | DEV-35615 | Physician Portal | 7.x-MaintenanceTriage | Not Reproducible | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
4 | 19 | impetus_sprint19 | DEV-33558 | Charge Capture | 7.6.1 | Verified | Closed | Praveen Kumar | Swati Narang |  | sprint18 |  | 0.8 | 1 | 1 | 2 | 2
5 | 19 | impetus_sprint19 | DEV-32577 | Sign Out | 7.6.1 | Verified | Closed | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 1 | 1
6 | 19 | impetus_sprint19 | DEV-30955 | Charge Capture | Declined Issues | Not Reproducible | Closed | Suhani Aneja |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
7 | 19 | impetus_sprint19 | DEV-30367 | Charge Capture | 7.6.1 | Verified | Closed | Kumar Saurabh | Swati Narang |  |  |  | 2 | 2 | 2 | 3 | 3
8 | 19 | impetus_sprint19 | DEV-27612 | Desktop Clinical Results | Declined Issues | Working as Designed | Closed | Abhishek Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
9 | 19 | impetus_sprint19 | DEV-25921 | Admin Tools | 760FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand |  | sprint18 |  | 2 | 2 | 1 | 3 | 2
10 | 19 | impetus_sprint19 | DEV-20824 | Dispatcher | 7.x-MaintenanceTriage | Obsolete | Final Review | Kumar Saurabh |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
11 | 19 | impetus_sprint19 | DEV-17562 | Charge Capture | 7.6.1 | Not Reproducible | Closed | Suhani Aneja |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
12 | 19 | impetus_sprint19 | DEV-10616 | Code Edits | Declined Issues | Known Issue | Closed | Suhani Aneja |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
13 | 19 | impetus_sprint19 | DEV-9377 | Admin Tools | Future - to be scheduled | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
1 | 20 | impetus_sprint20 | DEV-37052 | Charge Capture | 7.6.1 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
2 | 20 | impetus_sprint20 | DEV-37008 | Charge Capture | 7.6.0.3 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 1 | 1
3 | 20 | impetus_sprint20 | DEV-36994 | Admin Tools | 7.6.1 | Verified | Closed | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
4 | 20 | impetus_sprint20 | DEV-35875 | Admin Tools, Charge Capture | Declined Issues | Working as Designed | Closed | Sameer Panda |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
5 | 20 | impetus_sprint20, vitals | DEV-35797 | Desktop Clinical Results | 7.6.1 | Verified | Closed | Suhani Aneja | Nitin Anand |  | sprint19 |  | 1 | 1 | 1 | 2 | 2
6 | 20 | impetus_sprint20 | DEV-35027 | NoteWriter | Declined Issues | Declined | Closed | Abhishek Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
7 | 20 | impetus_sprint20 | DEV-34663 | iPhone | 7.6.1 | Verified | Closed | Praveen Kumar | Swati Narang |  | sprint18 |  | 1 | 1 | 1 | 3 | 3
8 | 20 | impetus_sprint20 | DEV-33917 | NoteWriter | 7.6.1 | Declined | Closed | Praveen Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
9 | 20 | impetus_sprint20 | DEV-31661 | Charge Capture | 7.6.1 | Verified | Closed | Kumar Saurabh | Swati Narang |  | sprint19 |  | 1 | 1 | 1 | 2 | 2
10 | 20 | impetus_sprint20 | DEV-28232 | Upgrades | 7.6.1 | Verified | Closed | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
11 | 20 | impetus_sprint20 | DEV-26771 | Admin Tools, System/Mobilizer | 7.x-MaintenanceTriage | Duplicate | Nothing to Fix | Praveen Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
12 | 20 | impetus_sprint20 | DEV-22001 | Charge Capture | 7.6.1 | Unresolved | Open | Suhani Aneja |  | This was put on hold, so we need to include the size in this sprint as there was 3 days effort put into this | sprint19 |  | 2 | 2 |  | 3 | 3
13 | 20 | impetus_sprint20 | DEV-18013 | Admin Tools, Other (not included in this list) | 7.6.1 | Workaround Provided | Nothing to Fix | Praveen Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
14 | 20 | impetus_sprint20 | DEV-13095 | Admin Tools | 760FFD | Declined | Closed | Sameer Panda |  |  | sprint19 |  | 1 | 2 | 2 | 2 | 4
15 | 20 | impetus_sprint20 | DEV-12196 | Charge Capture | 7.6.1 | Verified | Closed | Suhani Aneja | Nitin Anand |  |  |  | 1 | 2 | 2 | 2 | 3
16 | 20 | impetus_sprint20 | DEV-10658 | Charge Capture | 7.6.1 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
1 | 21 | impetus_Sprint21 | DEV-37003 | Manual Registration | 76x_FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 1 | 1 | 2
2 | 21 | impetus_Sprint21 | DEV-36992 | Charge Capture | Declined Issues | Working as Designed | Final Review | Kumar Saurabh |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
3 | 21 | impetus_Sprint21 | DEV-36727 | Charge Capture | 76x_FFD | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 1 | 1
4 | 21 | impetus_sprint21 | DEV-36637 | Physician Portal | 7.6.1 | Verified | Closed | Praveen Kumar | Swati Narang |  |  |  | 2 | 2 | 2 | 3 | 3
5 | 21 | impetus_sprint21 | DEV-36531 | Charge Capture | Declined Issues | Known Issue | Closed | Suhani Aneja |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
6 | 21 | impetus_Sprint21 | DEV-35728 | Charge Capture | 76x_FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
7 | 21 | impetus_sprint21 | DEV-34592 | Desktop Clinical Results | 7.6.1 | Duplicate | Closed | Praveen Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
8 | 21 | impetus_Sprint21 | DEV-34211 | Charge Capture | 76x_FFD | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
9 | 21 | impetus_sprint21 | DEV-30651 | Physician Portal | 76x_FFD | Verified | Closed | Suhani Aneja | Nitin Anand |  | sprint20 |  | 1 | 1 | 1 | 1 | 1
10 | 21 | impetus_sprint21 | DEV-24206 | Charge Capture | 76x_FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
11 | 21 | impetus_sprint21 | DEV-22626 | Physician Portal | 7.6.1 | Verified | Closed | Praveen Kumar | Swati Narang |  | sprint18 |  | 1 | 2 | 2 | 3 | 3
12 | 21 | impetus_Sprint21 | DEV-21760 | Admin Tools | 76x_FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
13 | 21 | impetus_Sprint21 | DEV-21254 | System/Mobilizer | 76x_FFD | Not Reproducible | Final Review | Kumar Saurabh |  |  |  |  | 1 | 1 | 1 | 2 | 2
14 | 21 | impetus_sprint21 | DEV-17844 | Charge Capture | 76x_FFD | Obsolete | Final Review | Praveen Kumar |  |  |  |  | 2 | 2 | 2 | 3 | 3
15 | 21 | impetus_sprint21 | DEV-13238 | Admin Tools | 7.6.1 | Verified | Closed | Praveen Kumar | Nitin Anand |  | sprint18 |  | 1 | 2 | 2 | 3 | 3
16 | 21 | impetus_sprint21 | DEV-11388 | Installation | 76x_FFD | Unresolved | Testing | Abhishek Kumar |  |  |  |  | 1 | 1 |  | 2
17 | 21 | impetus_Sprint21 | DEV-7967 | Other (not included in this list) | Declined Issues | Obsolete | Closed | Kumar Saurabh |  |  |  |  | 1 | 1 | 1 | 1 | 1
1 | 22 | impetus_sprint22 | DEV-37227 | Physician Portal | 76x_FFD | Duplicate | Nothing to Fix | Abhishek Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
2 | 22 | impetus_sprint22 | DEV-37184 | Admin Tools | 76x_FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
3 | 22 | impetus_sprint22 | DEV-37172 | Admin Tools | 76x_FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
4 | 22 | impetus_sprint22 | DEV-36185 | Dispatcher | 76x_FFD | Unresolved | Testing | Praveen Kumar |  |  |  |  | 2 | 2 |  | 2
5 | 22 | impetus_sprint22 | DEV-35987 | Charge Capture | 76x_FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 2 | 2 | 3
6 | 22 | Dragon, impetus_sprint22 | DEV-35574 | NoteWriter | Declined Issues | Declined | Closed | Kumar Saurabh |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
7 | 22 | impetus_sprint22 | DEV-32643 | Charge Capture | 76x_FFD | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
8 | 22 | impetus_sprint22 | DEV-28107 | Upgrades | 76x_FFD | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 2 | 1 | 2
9 | 22 | HCA_6Admin, impetus_sprint22 | DEV-27647 | Admin Tools | 76x_FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
10 | 22 | impetus_sprint22 | DEV-24564 | eSignature | Declined Issues | Declined | Closed | Kumar Saurabh |  |  |  |  | 0.8 | 0.8 | 1 | 1 | 1
11 | 22 | Partners, impetus_sprint22 | DEV-19466 | Admin Tools, Code Edits | 76x_FFD | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 1 | 1
12 | 22 | impetus_sprint22 | DEV-16718 | Charge Capture | 76x_FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
13 | 22 | impetus_sprint22 | DEV-16392 | System/Mobilizer | Declined Issues | Obsolete | Closed | Abhishek Kumar |  |  |  |  | 1 | 1 | 1 | 1 | 1
14 | 22 | impetus_sprint22 | DEV-16349 | Charge Capture | 76x_FFD | Unresolved | In Progress | Praveen Kumar |  |  |  |  | 2 | 2 |  | 4
15 | 22 | impetus_sprint22 | DEV-11388 | Installation | 76x_FFD | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 2 | 3 | 3
16 | 22 | impetus_sprint22 | DEV-10319 | Charge Capture | 76x_FFD | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 2 | 2 |  | 3
17 | 22 | impetus_sprint22 | DEV-10032 | Charge Capture | 76x_FFD | Unresolved | Initial Review | Praveen Kumar
1 | 23 | impetus_sprint23 | DEV-37192 | Desktop Clinical Results, Physician Portal | 7.x_NextGenCC Phase 2 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
2 | 23 | impetus_sprint23 | DEV-36446 | Charge Capture | Declined Issues | Duplicate | Closed | Praveen Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
3 | 23 | impetus_sprint23 | DEV-36185 | Dispatcher | 7.x_NextGenCC Phase 2 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 2 | 2 | 2 | 4 | 4
4 | 23 | impetus_sprint23 | DEV-35462 | Physician Portal | 76x_FFD | Unresolved | In Progress | Ankit Verma |  |  |  |  | 2 | 2 |  | 3
5 | 23 | impetus_sprint23 | DEV-32527 | Admin Tools | 7.x_NextGenCC Phase 2 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 2 | 2 | 2 | 3 | 4
6 | 23 | impetus_sprint23 | DEV-32341 | Charge Capture | Declined Issues | Obsolete | Closed | Praveen Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
7 | 23 | impetus_sprint23 | DEV-30930 | Desktop Clinical Results | 7.x_NextGenCC Phase 2 | Unresolved | Testing | Abhishek Kumar |  |  |  |  | 2 | 2 |  | 3
8 | 23 | impetus_sprint23 | DEV-25269 | Code Edits | 7.6.2 | Obsolete | Closed | Suhani Aneja |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
9 | 23 | impetus_sprint23 | DEV-20932 | Provider Directory | Declined Issues | Declined | Nothing to Fix | Suhani Aneja |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
10 | 23 | impetus_sprint23 | DEV-19203 | Sign-Out | 7.x_NextGenCC Phase 2 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 2 | 2 | 2 | 4 | 4
11 | 23 | impetus_sprint23 | DEV-18426 | Auditing | Declined Issues | Working as Designed | Closed | Kumar Saurabh |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
12 | 23 | impetus_sprint23 | DEV-16103 | Admin Tools | 7.x_NextGenCC Phase 2 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 2 | 2 | 2 | 4
13 | 23 | impetus_sprint23 | DEV-13720 | Charge Capture | 76x_FFD | Unresolved | Testing | Suhani Aneja |  |  |  |  | 2 | 2 |  | 3
14 | 23 | impetus_sprint23 | DEV-13479 | Admin Tools | 7.x_NextGenCC Phase 2 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 2 | 3 | 4
15 | 23 | impetus_sprint23 | DEV-12626 | Charge Capture | 7.x_NextGenCC Phase 2 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 2 | 2 | 2 | 4 | 4
16 | 23 | HCA_7Portal2, hca_uncategorized, impetus_sprint23 | DEV-11304 | Desktop Clinical Results | 7.x-MaintenanceTriage | Duplicate | Final Review | Ankit Verma |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
17 | 23 | impetus_sprint23 | DEV-10310 | Desktop Clinical Results | 76x_FFD | Duplicate | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
1 | 24 | impetus_sprint24 | DEV-37906 | Desktop Clinical Results | 7.6.2.1 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
2 | 24 | impetus_sprint24 | DEV-37143 | Physician Portal | 76x_FFD | Unresolved | In Progress | Ankit Verma |  |  |  |  | 1 | 1 |  | 2
3 | 24 | impetus_sprint24 | DEV-36226 | NoteWriter | Declined Issues | Working as Designed | Closed | Ankit Verma |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
4 | 24 | impetus_sprint24 | DEV-35611 | NoteWriter | 7.7.0 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 1 | 1
5 | 24 | impetus_sprint24 | DEV-35462 | Physician Portal | 76x_FFD | Verified | Final Review | Ankit Verma | Nitin Anand |  |  |  | 2 | 2 | 2 | 3 | 3
6 | 24 | impetus_sprint24 | DEV-33551 | Charge Capture | 7.x_NextGenCC Phase 2 | Verified | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 2 | 2 | 2 | 3 | 3
7 | 24 | impetus_sprint24 | DEV-30930 | Desktop Clinical Results | 7.x_NextGenCC Phase 2 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 2 | 2 | 2 | 3 | 3
8 | 24 | impetus_Sprint24 | DEV-30541 | NoteWriter | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
9 | 24 | impetus_sprint24 | DEV-28911 | NoteWriter | 7.7.0 | Not Reproducible | Final Review | Praveen Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
10 | 24 | impetus_sprint24 | DEV-28656 | NoteWriter | 7.7.0 | Not Reproducible | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
11 | 24 | impetus_sprint24 | DEV-27463 | NoteWriter | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
12 | 24 | impetus_Sprint24 | DEV-27347 | NoteWriter | 7.x-MaintenanceTriage | Not Reproducible | Final Review | Ankit Verma | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
13 | 24 | impetus_sprint24 | DEV-23745 | NoteWriter | 7.7.0 | Not Reproducible | Final Review | Ankit Verma |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
14 | 24 | impetus_sprint24 | DEV-23471 | NoteWriter | 7.7.0 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
15 | 24 | impetus_sprint24 | DEV-22336 | System/Mobilizer | 7.7.0 | Obsolete | Final Review | Kumar Saurabh |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
16 | 24 | impetus_sprint24 | DEV-21694 | NoteWriter, Problem List | Declined Issues | Working as Designed | Nothing to Fix | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
17 | 24 | impetus_Sprint24 | DEV-19790 | NoteWriter | Declined Issues | Obsolete | Nothing to Fix | Kumar Saurabh | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
18 | 24 | impetus_sprint24 | DEV-13720 | Charge Capture | 76x_FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 2 | 2 | 2 | 3 | 3
19 | 24 | impetus_sprint24 | DEV-10398 | Forms | 7.7.0 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 1 | 1
20 | 24 | impetus_sprint24 | DEV-10319 | Charge Capture | 76x_FFD | Unresolved | In Progress | Suhani Aneja |  | 5(Sprint22 and Sprint23 3days + Sprint24 2 days) |  |  | 3 | 3 |  | 5
1 | 25 | demo, impetus_sprint25, notewriter | DEV-37934 | NoteWriter | 7.7.0 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
2 | 25 | Partners, impetus_Sprint25 | DEV-37535 | Charge Capture | 7.x Phase 2 MR | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 2 |  |  | 3
3 | 25 | impetus_sprint25, medications | DEV-37338 | iPhone, Mobile Clinical Results | 7.7.0 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 1 |  |  | 2
4 | 25 | impetus_Sprint25 | DEV-35272 | NoteWriter | 7.7.0 | Unresolved | Testing | Suhani Aneja |  |  |  |  | 0.8 |  |  | 1
5 | 25 | impetus_Sprint25 | DEV-28716 | NoteWriter | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
6 | 25 | impetus_sprint25 | DEV-27804 | Charge Capture, NoteWriter | 7.7.0 | Not Reproducible | Final Review | Kumar Saurabh | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
7 | 25 | impetus_sprint25 | DEV-27798 | Charge Capture, NoteWriter | 7.7.0 | Not Reproducible | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
8 | 25 | impetus_sprint25 | DEV-27408 | NoteWriter | 7.7.0 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
9 |  | impetus_sprint25 | DEV-27352 | NoteWriter | 7.7.0 | Not Reproducible | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
10 | 25 | impetus_sprint25 | DEV-26921 | NoteWriter | 7.7.0 | Not Reproducible | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
11 | 25 | impetus_sprint25 | DEV-26840 | NoteWriter | Declined Issues | Obsolete | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
12 | 25 | impetus_sprint25 | DEV-23611 | NoteWriter | Declined Issues | Obsolete | Final Review | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
13 | 25 | impetus_sprint25 | DEV-23512 | NoteWriter | Declined Issues | Obsolete | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
14 | 25 | impetus_sprint25 | DEV-23482 | NoteWriter | 7.7.0 | Not Reproducible | Final Review | Ankit Verma | Nitin Anand |  |  |  | 1 | 1 | 1 | 1 | 1
15 | 25 | impetus_sprint25 | DEV-23469 | NoteWriter | 7.7.0 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
16 | 25 | impetus_Sprint25 | DEV-23402 | NoteWriter | Declined Issues | Declined | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
17 | 25 | impetus_sprint25 | DEV-21992 | NoteWriter | 7.7.0 | Not Reproducible | Final Review | Ankit Verma | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 1
18 | 25 | impetus_Sprint25 | DEV-21941 | NoteWriter | Declined Issues | Obsolete | Nothing to Fix | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
19 | 25 | impetus_sprint25 | DEV-21878 | Manual Registration, NoteWriter | Declined Issues | Known Issue | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
20 | 25 | impetus_sprint25 | DEV-21867 | NoteWriter | Declined Issues | Obsolete | Final Review | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
1 | 26 | demo, impetus_sprint26, notewriter | DEV-37935 | NoteWriter | 7.6.5 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
2 | 26 | impetus_sprint26 | DEV-37930 | NoteWriter, Problem List | 7.6.5 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
3 | 26 | demo, impetus_sprint26, notewriter | DEV-37923 | NoteWriter | 7.6.5 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
4 | 26 | demo, impetus_sprint26, notewriter | DEV-37921 | NoteWriter | 7.6.5 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
5 | 26 | impetus_sprint26 | DEV-37906 | Desktop Clinical Results | 7.6.2.1 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
6 | 26 | impetus_sprint26 | DEV-37879 | Desktop Clinical Results, Physician Portal | 7.6.3 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
7 | 26 | impetus_sprint26 | DEV-37581 | NoteWriter | 7.6.5 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 0.8 |  |  | 1
8 | 26 | Partners, impetus_sprint26 | DEV-37535 | Charge Capture | 7.6.4.1 | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 2 |  |  | 3
9 | 26 | impetus_sprint26, medications | DEV-37338 | iPhone, Mobile Clinical Results | 7.7.0 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
10 | 26 | impetus_sprint26 | DEV-37262 | Admin Tools | 7.7.0 | Obsolete | Nothing to Fix | Ankit Verma |  |  |  |  | 1 | 1 | 1 | 1 | 1
11 | 26 | impetus_sprint26 | DEV-37143 | Physician Portal | 7.7.0 | Verified | Final Review | Ankit Verma | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
12 | 26 | impetus_sprint26, notewriter | DEV-36876 | NoteWriter | 7.6.5 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 2 | 2 | 2 | 4
13 | 26 | Phase2_GA, impetus_sprint26 | DEV-36727 | Charge Capture | 7.6.4 | Verified | Closed | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
14 | 26 | Phase2_GA, impetus_sprint26 | DEV-35383 | Manual Registration | 7.6.4 | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 2 |  | 3
15 | 26 | PM_clarification_needed, impetus_sprint26 | DEV-35272 | NoteWriter | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 1 | 1 | 1
16 | 26 | impetus_sprint26 | DEV-30930 | Desktop Clinical Results | 7.6.4 | Verified | Closed | Abhishek Kumar | Nitin Anand |  |  |  | 2 | 2 | 2 | 3 | 3
17 | 26 | impetus_sprint26 | DEV-30738 | NoteWriter | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
18 | 26 | impetus_sprint26 | DEV-29783 | NoteWriter | 7.7.0 | Obsolete | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
19 | 26 | impetus_sprint26 | DEV-28555 | NoteWriter | 7.7.0 | Unresolved | In Progress | Ankit Verma |  |  |  |  | 1 |  |  | 2
20 | 26 | impetus_sprint26 | DEV-27819 | Charge Capture, NoteWriter | 7.7.0 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
21 | 26 | impetus_sprint26 | DEV-27346 | NoteWriter | 7.7.0 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 1 | 1
22 | 26 | impetus_sprint26 | DEV-23467 | NoteWriter | Declined Issues | Declined | Final Review | Ankit Verma | Nitin Anand |  |  |  | 1 | 1 | 1 | 1 | 1
23 | 26 | impetus_sprint26 | DEV-23454 | NoteWriter | 7.6.5 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
24 | 26 | impetus_sprint26 | DEV-21864 | NoteWriter | 7.7.0 | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 1 |  |  | 2
1 | 27 | impetus_Sprint27 | DEV-38640 | Admin Tools | 7.6.5 | Testing | In Progress | Ankit Verma |  |  |  |  | 2 | 2 |  | 2
2 | 27 | impetus_sprint27 | DEV-37928 | NoteWriter | 7.6.5 | Obsolete | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
3 | 27 | impetus_sprint27 | DEV-37351 | NoteWriter | 7.7.0 | Working as Designed | Final Review | Abhishek Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
4 | 27 | impetus_sprint27 | DEV-23846 | NoteWriter | Declined Issues | Declined | Final Review | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
5 | 27 | impetus_sprint27 | DEV-37876 | Desktop Clinical Results | 7.6.5 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
6 | 27 | impetus_sprint27 | DEV-37195 | Charge Capture | 7.6.5 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 1 | 1
7 | 27 | impetus_Sprint27 | DEV-28961 | NoteWriter | 7.6.5 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 1 | 1 |  | 1
8 | 27 | impetus_Sprint27 | DEV-37581 | Admin Tools | 7.6.5 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 1 |  |  | 2
9 | 27 | Partners, impetus_sprint27 | DEV-37535 | Charge Capture | 7.6.5 | Unresolved | In Progress | Suhani Aneja |  |  | Sprint26 |  | 2 |  |  | 3
10 | 27 | Phase2_GA, impetus_sprint27 | DEV-35383 | Manual Registration | 7.6.5 | Unresolved | In Progress | Suhani Aneja |  |  | Sprint26 |  | 2 |  |  | 3
11 | 27 | impetus_sprint27 | DEV-21864 | NoteWriter | 7.7.0 | Unresolved | In Progress | Suhani Aneja |  |  | Sprint26 |  | 1 |  |  | 2
12 | 27 | impetus_sprint27 | DEV-37235 | NoteWriter | 7.6.6 | Unresolved | Initial Review | Abhishek Kumar |  |  |  |  | 2 |  |  | 3
13 | 27 | impetus_sprint27 | DEV-37925 | NoteWriter | 7.6.6 | Unresolved | In Progress | Praveen Kumar |  |  |  |  | 1 |  |  | 1
1 | 28 | impetus_sprint28 | DEV-38640 | Admin Tools, Other (not included in this list) | 7.6.5 | Unresolved | Testing | Ankit Verma |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
2 | 28 | impetus_sprint28 | DEV-38633 | Charge Capture | 7.6.5 | Not Reproducible | Closed | Suhani Aneja |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
3 | 28 | impetus_sprint28 | DEV-38630 | Admin Tools | 7.6.5 | Verified | Closed | Ankit Verma |  |  |  |  | 1 | 1 | 1 | 1 | 1
4 | 28 | impetus_sprint28 | DEV-38524 | Charge Capture | 7.6.5 | Verified | Closed | Praveen Kumar |  |  |  |  | 1 | 1 | 1 | 1 | 1
5 | 28 | impetus_sprint28 | DEV-38507 | Charge Capture | 7.6.5 | Verified | Closed | Praveen Kumar |  |  |  |  | 1 | 1 | 1 | 1 | 1
6 | 28 | impetus_sprint28 | DEV-38466 | Charge Capture, Problem List | 7.6.5 | Working as Designed | Final Review | Kumar Saurabh |  |  |  |  | 1 | 1 | 1 | 1 | 1
7 | 28 | impetus_sprint28 | DEV-38387 | Charge Capture, System/Mobilizer | 7.6.6 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 1 | 1
8 | 28 | impetus_sprint28 | DEV-38172 | Auditing | 7.7.0 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 2 |  |  | 3
9 | 28 | impetus_sprint28 | DEV-38042 | Problem List | 7.6.6 | Unresolved | In Progress | Kumar Saurabh |  |  |  |  | 1 |  |  | 2
10 | 28 | impetus_sprint28 | DEV-37984 | Charge Capture | 7.6.5 | Verified | Final Review | Ankit Verma | Nitin Anand |  |  |  | 1 | 1 | 1 | 1 | 2
11 | 28 | impetus_sprint28 | DEV-37581 | NoteWriter | 7.6.6 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 2 | 2 | 2 | 3
12 | 28 | impetus_sprint28 | DEV-37580 | Desktop Clinical Results | 7.6.6 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
13 | 28 | impetus_sprint28 | DEV-37450 | Admin Tools | 7.6.6 | Verified | Final Review | Ankit Verma | Nitin Anand |  |  |  | 1 | 1 | 1 | 1 | 1
14 | 28 | Partners, impetus_sprint28 | DEV-37303 | Charge Capture | 7.6.5 | Unresolved | Revisit | Praveen Kumar |  |  |  |  | 2 |  |  | 4
15 | 28 | impetus_sprint28 | DEV-37235 | NoteWriter | 7.6.6 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 2 |  |  | 2
16 | 28 | impetus_sprint28 | DEV-37196 | Patient List | 7.6.6 | Obsolete | Nothing to Fix | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 1 | 1
17 | 28 | impetus_sprint28 | DEV-36719 | Desktop Clinical Results | 7.6.6 | Unresolved | In Progress | Ankit Verma |  |  |  |  | 1 |  |  | 2
18 | 28 | Phase2_GA, impetus_sprint28 | DEV-35383 | Manual Registration | 7.6.5 | Verified | Final Review | Suhani Aneja |  |  | Sprint26 |  | 2 | 2 | 2 | 4 | 4
19 | 28 | impetus_sprint28 | DEV-28961 | NoteWriter | 7.6.6 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 0.8 |  |  | 1
20 | 28 | impetus_sprint28 | DEV-21864 | NoteWriter | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  | Sprint26 |  | 1 | 1 | 1 | 2 | 2
21 | 28 | impetus_sprint28 | DEV-17600 | Forms, PQRS | 7.6.6 | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 1 |  |  | 2
22 | 28 | impetus_sprint28 | DEV-10319 | Charge Capture | 7.6.6 | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 2 |  |  | 3
1 | 29 | impetus_sprint29 | DEV-38785 | Physician Portal | 7.7.0 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 1 |  |  | 2
2 | 29 | impetus_sprint29 | DEV-38700 | Charge Capture | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
3 | 29 | impetus_sprint29 | DEV-38658 | Charge Capture | 7.6.5 | Verified | Closed | Praveen Kumar |  |  |  |  | 1 | 1 | 1 | 1 | 1
4 | 29 | impetus_sprint29 | DEV-38657 | Charge Capture | 7.6.5 | Verified | Closed | Praveen Kumar |  |  |  |  | 1 | 1 | 1 | 1 | 1
5 | 29 | impetus_sprint29 | DEV-38655 | Manual Registration | 7.6.5 | Verified | Closed | Suhani Aneja |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
6 | 29 | impetus_sprint29 | DEV-38598 | CPOE | 7.7.0 | Unresolved | Open | Kumar Saurabh |  |  |  |  | 1 |  |  | 2
7 | 29 | impetus_sprint29 | DEV-38566 | CPOE | 7.7.0 | Unresolved | Open | Praveen Kumar |  |  |  |  | 1 |  |  | 2
8 | 29 | impetus_sprint29 | DEV-38526 | Charge Capture | 7.6.5 | Verified | Closed | Praveen Kumar |  |  |  |  | 1 | 1 | 1 | 1 | 1
9 | 29 | impetus_sprint29 | DEV-38172 | Auditing | 7.7.0 | Unresolved | Testing | Abhishek Kumar |  |  |  |  | 2 |  |  | 4
10 | 29 | impetus_sprint29 | DEV-38042 | Problem List | 7.7.0 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
11 | 29 | impetus_sprint29 | DEV-38008 | Charge Capture | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
12 | 29 | impetus_sprint29 | DEV-37959 | Admin Tools | 7.7.0 | Verified | Final Review | Ankit Verma | Nitin Anand |  |  |  | 1 | 1 | 1 | 1 | 1
13 | 29 | demo, impetus_sprint29 | DEV-37925 | NoteWriter | 7.6.6 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 2 | 2 | 2 | 4 | 4
14 | 29 | impetus_sprint29 | DEV-37696 | Admin Tools | 7.7.0 | Unresolved | Testing | Kumar Saurabh |  |  |  |  | 1 |  |  | 2
15 | 29 | impetus_sprint29 | DEV-37604 | Admin Tools | 7.7.0 | Declined | Nothing to Fix | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
16 | 29 | Partners, impetus_sprint29 | DEV-37303 | Charge Capture | 7.6.5 | Verified | Closed | Praveen Kumar |  |  |  |  | 2 | 2 | 2 | 4 | 4
17 | 29 | impetus_sprint29 | DEV-37235 | NoteWriter | 7.6.6 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 2 |  |  | 4
18 | 29 | impetus_sprint29 | DEV-36719 | Desktop Clinical Results | 7.6.6 | Unresolved | In Progress | Ankit Verma |  |  |  |  | 1 |  |  | 2
19 | 29 | impetus_sprint29 | DEV-32286 | CPOE | 7.7.0 | Obsolete | Nothing to Fix | Ankit Verma | Nitin Anand |  |  |  | 1 | 1 | 1 | 1 | 1
20 | 29 | impetus_sprint29 | DEV-17600 | Forms, PQRS | 7.6.6 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
21 | 29 | impetus_sprint29 | DEV-9396 | Charge Capture | 7.7.0 | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 2 |  |  | 3
1 | 30 | impetus_sprint30 | DEV-38818 | Admin Tools | 7.7.0 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
2 | 30 | impetus_sprint30 | DEV-38796 | Charge Capture | 7.x ICD10 | Not Reproducible | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
3 | 30 | impetus_sprint30 | DEV-38785 | Physician Portal | 7.7.0 | Verified | Final Review | Abhishek Kumar | Swati Narang |  |  |  | 1 | 2 | 2 | 2 | 3
4 | 30 | impetus_sprint30 | DEV-38702 | Physician Portal | 7.7.0 | Unresolved | In Progress | Ankit Verma |  |  |  |  | 1 |  |  | 1
5 | 30 | impetus_sprint30 | DEV-38598 | CPOE | 7.7.0 | Config Issue - Undocumented | Nothing to Fix | Kumar Saurabh | Swati Narang |  |  |  | 1 | 2 | 2 | 2 | 3
6 | 30 | impetus_sprint30 | DEV-38566 | CPOE | 7.7.0 | Unresolved | Open | Praveen Kumar
7 | 30 | impetus_sprint30 | DEV-38172 | Auditing | 7.7.0 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 2 | 2 | 2 | 3 | 4
8 | 30 | impetus_sprint30 | DEV-37944 | Desktop Clinical Results | 7.7.0 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 1 | 1
9 | 30 | impetus_sprint30 | DEV-37943 | Admin Tools | 7.7.0 | Unresolved | In Progress | Ankit Verma
10 | 30 | impetus_sprint30 | DEV-37942 | Physician Portal | 7.7.0 | Unresolved | In Progress | Ankit Verma |  |  |  |  | 2 | 2 | 2 | 3 | 3
11 | 30 | impetus_sprint30 | DEV-37696 | Admin Tools | 7.7.0 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 2 | 2 | 3 | 3
12 | 30 | impetus_sprint30 | DEV-37562 | Charge Capture | 7.7.0 | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 1 |  |  | 2
13 | 30 | impetus_sprint30 | DEV-37499 | Admin Tools | 7.7.0 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
14 | 30 | impetus_sprint30 | DEV-37237 | Admin Tools | 7.7.0 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
15 | 30 | impetus_sprint30 | DEV-37235 | NoteWriter | 7.6.6 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 2 |  |  | 3
16 | 30 | impetus_sprint30 | DEV-37142 | Admin Tools, Sign-Out | 7.6.6 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 2 | 2 | 2 | 3 | 3
17 | 30 | impetus_sprint30 | DEV-37111 | Admin Tools | 7.7.0 | Not Reproducible | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
18 | 30 | impetus_sprint30 | DEV-37108 | Physician Portal | 7.7.0 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 0.8 |  |  | 1
19 | 30 | impetus_sprint30 | DEV-36379 | CPOE | 7.6.6 | Unresolved | Testing | Abhishek Kumar |  |  |  |  | 1 |  |  | 2
20 | 30 | impetus_sprint30 | DEV-35025 | Charge Capture | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 2 | 2 | 2
21 | 30 | impetus_sprint30 | DEV-31691 | Charge Capture, PQRS | 7.7.0 | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 2 |  |  | 3
22 | 30 | impetus_sprint30 | DEV-9396 | Charge Capture | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 2 | 2 | 2 | 3 | 3
1 | 31 | demo, impetus_sprint31 | DEV-38999 | NoteWriter, Physician Portal | 7.6.6 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 1 |  |  | 2
2 | 31 | impetus_sprint31, portal | DEV-38998 | Physician Portal | 7.6.6 | Verified | Final Review | Praveen Kumar |  |  |  |  | 1 | 1 | 1 | 1 | 1
3 | 31 | Partners, impetus_sprint31 | DEV-38958 | Charge Capture | 7.6.5.1 | Verified | Final Review | Praveen Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
4 | 31 | impetus_sprint31 | DEV-38956 | Charge Capture | 7.6.5.1 | Verified | Final Review | Praveen Kumar |  |  |  |  | 2 | 2 | 2 | 4 | 4
5 | 31 | impetus_sprint31 | DEV-38887 | NoteWriter | 7.6.6 | Verified | Final Review | Abhishek Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
6 | 31 | impetus_sprint31 | DEV-38702 | Physician Portal | 7.7.0 | Verified | Final Review | Ankit Verma |  |  |  |  | 1 | 1 | 1 | 1 | 1
7 | 31 | impetus_sprint31 | DEV-38041 | Admin Tools | 7.7.0 | Verified | Final Review | Suhani Aneja |  |  |  |  | 1 | 1 | 1 | 2 | 2
8 | 31 | impetus_sprint31 | DEV-38008 | Charge Capture | 7.7.0 | Verified | Final Review | Suhani Aneja |  |  |  |  | 1 | 1 | 1 | 2 | 2
9 | 31 | impetus_sprint31 | DEV-37943 | Admin Tools | 7.7.0 | Unresolved | In Progress | Ankit Verma |  |  |  |  | 2 |  |  | 3
10 | 31 | impetus_sprint31 | DEV-37888 | Physician Portal | 7.7.0 | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 1 |  |  | 2
11 | 31 | impetus_sprint31 | DEV-37686 | Admin Tools | 7.6.6 | Duplicate | Nothing to Fix | Suhani Aneja |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
12 | 31 | impetus_sprint31 | DEV-37235 | NoteWriter | 7.6.6 | Unresolved | Testing | Abhishek Kumar |  |  |  |  | 3 |  |  | 4
13 | 31 | impetus_sprint31 | DEV-37108 | Physician Portal | 7.7.0 | Verified | Final Review | Abhishek Kumar |  |  |  |  | 1 | 1 | 2 | 2 | 2
14 | 31 | impetus_sprint31 | DEV-36846 | NoteWriter | Declined Issues | Known Issue | Closed | Kumar Saurabh |  |  |  |  | 1 | 1 | 1 | 2 | 2
15 | 31 | impetus_sprint31 | DEV-36719 | Desktop Clinical Results | 7.7.0 | Unresolved | In Progress | Ankit Verma |  |  |  |  | 2 |  |  | 2
16 | 31 | impetus_sprint31 | DEV-36351 | NoteWriter | 7.6.6 | Verified | Final Review | Praveen Kumar |  |  |  |  | 8 | 0.8 | 0.8 | 1 | 1
17 | 31 | Phase2_GA, impetus_sprint31 | DEV-35383 | Manual Registration | 7.6.5, 7.6.5.1 | Verified | Final Review | Suhani Aneja |  |  |  |  | 2 | 2 | 2 | 2 | 2
18 | 31 | impetus_sprint31 | DEV-32405 | Admin Tools | 7.7.0 | Verified | Final Review | Kumar Saurabh |  |  |  |  | 1 | 2 | 2 | 2 | 3
19 | 31 | impetus_sprint31 | DEV-31992 | CPOE | 7.6.6 | Verified | Final Review | Abhishek Kumar |  |  |  |  | 1 | 1 | 1 | 1 | 1
20 | 31 | impetus_sprint31 | DEV-31691 | Charge Capture, PQRS | 7.7.0 | Verified | Final Review | Suhani Aneja |  |  |  |  | 2 | 2 | 2 | 3 | 3
21 | 31 | hca_uncategorized, impetus_sprint31 | DEV-30724 | Desktop Clinical Results | 7.x-MaintenanceTriage | Unresolved | Initial Review | Kumar Saurabh |  |  |  |  | 1 |  |  | 3
22 | 31 | impetus_sprint31 | DEV-27212 | NoteWriter | 7.6.6 | Not Reproducible | Nothing to Fix | Ankit Verma |  |  |  |  | 1 | 1 | 1 | 1 | 1
23 | 31 | impetus_sprint31 | DEV-21783 | Admin Tools, NoteWriter | 7.6.6 | Unresolved | Open | Praveen Kumar |  |  |  |  | 2 |  |  | 3
24 | 31 | impetus_sprint31 | DEV-14391 | Schedule | 7.7.0 | Unresolved | Initial Review | Kumar Saurabh |  |  |  |  | 1 |  |  | 2
1 | 32 | impetus_sprint32 | DEV-39192 | Patient List | 7.6.6 | Not Reproducible | Final Review | Suhani Aneja | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
2 | 32 | impetus_sprint32 | DEV-39129 | Other (not included in this list) | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
3 | 32 | impetus_sprint32 | DEV-39119 | NoteWriter | 7.6.6 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
4 | 32 | impetus_sprint32 | DEV-39063 | Admin Tools | 7.7.0 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
5 | 32 | impetus_sprint32 | DEV-39039 | Admin Tools | 7.x-MaintenanceTriage | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 2 |  |  | 3
6 | 32 | impetus_sprint32, portal | DEV-39001 | Physician Portal | 7.6.6 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
7 | 32 | demo, impetus_sprint32 | DEV-38999 | NoteWriter, Physician Portal | 7.6.6 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
8 | 32 | impetus_DEV, impetus_sprint32 | DEV-38916 | Admin Tools | 7.7.0 | Verified | Final Review | Ankit Verma | Nitin Anand |  |  |  | 1 | 1 | 1 | 1 | 1
9 | 32 | impetus_sprint32 | DEV-38690 | Charge Capture, NoteWriter | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
10 | 32 | impetus_sprint32 | DEV-38662 | Visit Types | 7.7.0 | Unresolved | Initial Review | Praveen Kumar |  |  |  |  | 2 |  |  | 4
11 | 32 | impetus_DEV, impetus_sprint32 | DEV-38566 | CPOE | 7.7.0 | Unresolved | Open | Ankit Verma |  |  |  |  | 2 |  |  | 2
12 | 32 | impetus_sprint32 | DEV-37943 | Admin Tools | 7.7.0 | Verified | Final Review | Ankit Verma | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
13 | 32 | impetus_sprint32 | DEV-37888 | Physician Portal | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
14 | 32 | impetus_sprint32 | DEV-37235 | NoteWriter | 7.6.6 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 3 | 3 | 3 | 4 | 6
15 | 32 | impetus_sprint32, portal_facelift | DEV-37120 | Desktop Clinical Results | 7.6.6 | Verified | Final Review | Ankit Verma | Nitin Anand |  |  |  | 2 | 2 | 2 | 2 | 2
16 | 32 | impetus_sprint32 | DEV-35111 | Charge Capture | 7.x ICD10 | Obsolete | Nothing to Fix
17 | 32 | PM_clarification_needed, SpecNeeded, impetus_sprint32 | DEV-34046 | Messaging | Declined Issues | Declined | Nothing to Fix | Kumar Saurabh |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
18 | 32 | impetus_sprint32 | DEV-29222 | Admin Tools | Declined Issues | Declined | Nothing to Fix |  | Nitin Anand
19 | 32 | PM_clarification_needed, impetus_sprint32 | DEV-28961 | NoteWriter | 7.7.0 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 2 |  |  | 3
20 | 32 | impetus_sprint32 | DEV-27273 | Admin Tools | Declined Issues | Workaround Provided | Nothing to Fix | Abhishek Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
21 | 32 | impetus_sprint32 | DEV-23907 | Desktop Clinical Results | Declined Issues | Declined | Closed | Suhani Aneja |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
22 | 32 | impetus_sprint32 | DEV-23403 | NoteWriter | 7.7.0 | Not Reproducible | Nothing to Fix |  | Nitin Anand
23 | 32 | impetus_sprint32 | DEV-21783 | Admin Tools, NoteWriter | 7.6.6 | Verified | Final Review | Praveen Kumar |  |  |  |  | 2 | 2 | 2 | 4 | 4
24 | 32 | HCA_6Admin, impetus_sprint32 | DEV-19139 | Admin Tools, Architecture | 7.7.0 | Unresolved | In Progress | Kumar Saurabh |  |  |  |  | 3 |  |  | 5
25 | 32 | impetus_sprint32 | DEV-14391 | Schedule | 7.7.0 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
26 | 32 | impetus_sprint32 | DEV-12635 | Admin Tools | Declined Issues | Declined | Nothing to Fix |  | Swati Narang
1 | 33 | impetus_sprint33 | DEV-39404 | Charge Capture | 7.6.6 | Verified | Closed | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
2 | 33 | impetus_sprint33 | DEV-39379 | Desktop Clinical Results | 7.6.6 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
3 | 33 | impetus_QA_Identified, impetus_sprint33 | DEV-39329 | Meditech MIM Bridge | Declined Issues | Declined | Closed |  | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
4 | 33 | impetus_sprint33 | DEV-39273 | Desktop Clinical Results | 7.6.6 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
5 | 33 | impetus_QA_Identified, impetus_next, impetus_sprint33 | DEV-39228 | Auditing, Charge Capture, Code Edits | Declined Issues | Not Reproducible | Closed |  | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
6 | 33 | impetus_sprint33 | DEV-39185 | Other (not included in this list) | 7.7.0 | Verified | Final Review | Abhishek Kumar |  |  |  |  | 2 | 1 | 1 | 2 | 2
7 | 33 | demo, impetus_sprint33, notewriter | DEV-39162 | NoteWriter | 7.6.6 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
8 | 33 | impetus_sprint33 | DEV-39039 | Admin Tools | 7.7.0 | Unresolved | In Testing | Suhani Aneja |  |  |  |  | 2 |  |  | 3
9 | 33 | impetus_sprint33 | DEV-39026 | Admin Tools, Schedule | 7.6.6 | Verified | Final Review | Praveen Kumar | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
10 | 33 | impetus_sprint33 | DEV-38662 | Visit Types | 7.7.0 | Unresolved | Open | Praveen Kumar |  |  |  |  | 2 |  |  | 4
11 | 33 | impetus_sprint33 | DEV-37785 | Patient List | 7.6.6 | Verified | Closed | Praveen Kumar | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
12 | 33 | impetus_sprint33 | DEV-37350 | Other (not included in this list) | 7.7.0 | Unresolved | In Progress | Kumar Saurabh |  |  |  |  | 1 |  |  | 2
13 | 33 | impetus_sprint33 | DEV-31251 | Desktop Clinical Results | 7.7.0 | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 2 |  |  | 3
14 | 33 | impetus_sprint33 | DEV-29516 | Admin Tools | Declined Issues | Duplicate | Closed | Abhishek Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
15 | 33 | impetus_QA_Identified, impetus_sprint33 | DEV-28955 | Desktop Clinical Results | Declined Issues | Declined | Closed |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
16 | 33 | impetus_QA_Identified, impetus_sprint33 | DEV-27559 | Physician Portal | Declined Issues | Known Issue | Closed |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
17 | 33 | impetus_sprint33 | DEV-24695 | Desktop Clinical Results | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
18 | 33 | impetus_QA_Identified, impetus_sprint33 | DEV-24423 | Admin Tools | Declined Issues | Declined | Nothing to Fix |  | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
19 | 33 | impetus_sprint33 | DEV-21038 | Admin Tools, Desktop Clinical Results | 7.7.0 | Workaround Provided | Nothing to Fix | Abhishek Kumar |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
20 | 33 | impetus_sprint33 | DEV-18813 | Physician Portal | 7.7.0 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 2 |  |  | 2
21 | 33 | impetus_QA_Identified, impetus_sprint33 | DEV-18138 | Admin Tools | Declined Issues | Duplicate | Closed |  | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
22 | 33 | impetus_QA_Identified, impetus_sprint33 | DEV-17743 | Problem List | Declined Issues | Workaround Provided | Closed | [5 empty] | 0.8 | 0.8 | 0.8 | 1 | 1
23 | 33 | impetus_QA_Identified, impetus_sprint33 | DEV-14496 | Provider Directory | Declined Issues | Declined | Closed |  | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
24 | 33 | impetus_sprint33 | DEV-12516 | Auditing | 7.7.0 | Unresolved | In Progress | Ankit Verma |  |  |  |  | 1 |  |  | 2
25 | 33 | impetus_sprint33 | DEV-38566 | CPOE | 7.7.0 | Unresolved | In Progress | Ankit Verma |  |  |  |  | 1 |  |  | 2
26 | 33 | impetus_sprint33 | DEV-38886 | Admin Tools, Desktop Clinical Results | 7.7.0 | Unresolved | In Progress | Ankit Verma |  |  |  |  | 1 |  |  | 2
27 | 33 | impetus_sprint33 | DEV-26398 | Admin Tools | 7.7.0 | Unresolved | In Progress | Ankit Verma |  |  |  |  | 1 |  |  | 2
28 | 33 | impetus_sprint33 | DEV-10224 | Physician Portal | Future - to be scheduled | Duplicate | Nothing to Fix |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
29 | 33 | impetus_QA_Identified, impetus_sprint33 | DEV-9113 | Other (not included in this list) | Declined Issues | Workaround Provided | Closed |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
1 | 34 | impetus_sprint34 | DEV-39495 | Admin Tools | 7.7.0 | Verified | Final Review | Manoj Singh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
2 | 34 | impetus_sprint34 | DEV-39484 | Sign-Out | 7.6.8 | Unresolved | In Progress | Ankit Verma |  | I am currently working on this issue and for the single patient I am able to add the header on the second page of sign-out summary. But for multiple patients I am still working. |  |  | 2 |  |  | 3
3 | 34 | impetus_sprint34 | DEV-39477 | Sign-Out | 7.6.7 | Verified | Final Review | Manoj Singh | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
4 |  | impetus_sprint34 | DEV-39475 | Sign-Out | 7.6.8 | Unresolved | In Progress | Manoj Singh |  |  |  |  | 2 |  |  | 3
5 | 34 | impetus_sprint34 | DEV-39392 | CPOE | 7.6.7 | Verified | Final Review | Manoj Singh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
6 | 34 | impetus_sprint34 | DEV-39312 | Admin Tools | 7.7.0 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
7 | 34 | impetus_sprint34 | DEV-39284 | CPOE | 7.6.8 | Verified | Final Review | Suhani Aneja | Nitin Anand | Worked in Sprint 33 would be checked in Sprint 34 after 7.6.7 branch. | Sprint33 |  | 0.8 | 0.8 | 0.8 | 1 | 1
8 | 34 | impetus_sprint34 | DEV-39252 | NoteWriter | 7.6.7 | Verified | Final Review | Ankit Verma | Nitin Anand |  |  |  | 2 | 2 | 2 | 3 | 3
9 | 34 | impetus_sprint34, notewriter | DEV-39251 | NoteWriter | 7.6.7 | Obsolete | Closed |  | Swati Narang |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
10 | 34 | impetus_sprint34 | DEV-39240 | CPOE | 7.6.8 | Unresolved | Open | Praveen Kumar |  |  |  |  | 1 |  |  | 2
11 | 34 | impetus_sprint34 | DEV-39237 | CPOE | 7.6.8 | Verified | Final Review | Praveen Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
12 | 34 | impetus_sprint34 | DEV-39236 | CPOE | 7.6.8 | Verified | Final Review | Praveen Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
13 | 34 | impetus_sprint34 | DEV-39234 | CPOE | 7.6.8 | Unresolved | In Progress | Ankit Verma |  | Fixed at my end. For testing this issue I have done the routing setup and able to route the orders but still unable to test it exactly. |  |  | 1 |  |  | 2
14 | 34 | impetus_sprint34 | DEV-39039 | Admin Tools | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand | Worked in Sprint 33 Check in/Tested in Sprint 34 | Sprint33 |  | 2 | 2 | 2 | 3 | 3
15 | 34 | impetus_sprint34 | DEV-38894 | NoteWriter | 7.7.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
16 | 34 | impetus_sprint34 | DEV-38662 | Visit Types | 7.7.0 | Unresolved | Testing | Manoj Singh |  |  |  |  | 3 |  |  | 4
17 | 34 | impetus_sprint34 | DEV-37350 | Other (not included in this list) | 7.7.0 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
18 | 34 | impetus_sprint34 | DEV-37348 | Other (not included in this list) | 7.7.0 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
19 | 34 | impetus_sprint34 | DEV-36810 | NoteWriter | 7.7.0 | Unresolved | In Progress | Praveen Kumar |  |  |  |  | 2 |  |  | 3
20 | 34 | impetus_sprint34 | DEV-34166 | Desktop Clinical Results | 7.7.0 | Unresolved | In Progress | Abhishek Kumar |  | It’s almost completed but there is one minor issue remains for IE, discussed with John regarding some solution on that. I would say it’s not as easy as I thought. |  |  | 1 |  |  | 2
21 |  | impetus_sprint34 | DEV-32522 | Upgrades | 7.7.0 | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 0.8 |  |  | 1
22 | 34 | impetus_sprint34 | DEV-31351 | Desktop Clinical Results | 7.7.0 | Unresolved | In Progress | Suhani Aneja |  | Had sent mail for implementation perspective |  |  | 3 |  |  | 5
23 | 34 | impetus_sprint34 | DEV-31287 | Desktop Clinical Results | 7.7.0 | Unresolved | Initial Review | Abhishek Kumar |  |  |  |  | 3 |  |  | 5
24 | 34 | impetus_sprint34 | DEV-31251 | Desktop Clinical Results | 7.7.0 | Unresolved | In Progress | Suhani Aneja |  | Sprint 33(Points 2) | Sprint33 |  | 3 |  |  | 5
25 | 34 | impetus_sprint34 | DEV-28268 | Desktop Clinical Results, NoteWriter | 7.6.7 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 1 | 1
26 | 34 | impetus_sprint34 | DEV-26398 | Admin Tools | 7.7.0 | Unresolved | In Progress | Ankit Verma |  |  |  |  | 2 |  |  | 3
27 | 34 | impetus_sprint34 | DEV-22052 | System/Mobilizer | 7.7.0 | Unresolved | Open | Kumar Saurabh |  | Due to complexity of adding functionality to exclude users that is applied to different customization, discussed the different scenario’s with John. |  |  | 2 |  |  | 4
28 | 34 | impetus_sprint34 | DEV-18813 | Physician Portal | 7.7.0 | Verified | Final Review | Abhishek Kumar | Nitin Anand |  |  |  | 2 | 2 | 2 | 3 | 3
29 | 34 | impetus_sprint34 | DEV-12516 | Auditing | 7.7.0 | Verified | Final Review | Ankit Verma | Swati Narang |  |  |  | 1 | 1 | 1 | 2 | 2
1 | 35 | impetus_sprint35 | DEV-39725 | Admin Tools | 7.6.8 | Verified | Final Review | Praveen Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 1 | 1
2 | 35 | impetus_sprint35, notewriter | DEV-39663 | Admin Tools, NoteWriter | 7.6.8 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
3 | 35 | impetus_sprint35 | DEV-39662 | Admin Tools, NoteWriter | 7.6.8 | Duplicate | Nothing to Fix | [5 empty] | 0.8 | 0.8 | 0.8 | 1 | 1
4 | 35 | impetus_sprint35 | DEV-39661 | Admin Tools, NoteWriter | 7.6.8 | Unresolved | In Progress | Manoj Singh |  |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
5 | 35 | impetus_sprint35 | DEV-39660 | Admin Tools | 7.6.9 | Unresolved | In Progress | Ankit Verma |  |  |  |  | 1 |  |  | 1
6 | 35 | impetus_sprint35 | DEV-39659 | Admin Tools, NoteWriter | 7.6.8 | Unresolved | In Progress | Manoj Singh |  |  |  |  | 2 |  |  | 3
7 | 35 | impetus_sprint35 | DEV-39584 | Admin Tools | 7.6.8 | Verified | Final Review | Ankit Verma | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 3
8 | 35 | impetus_sprint35 | DEV-39574 | Admin Tools | 7.7.0 | Verified | Final Review | Kumar Saurabh | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
9 | 35 | impetus_sprint35 | DEV-39546 | Admin Tools | 7.7.0 | Verified | Final Review | Kumar Saurabh | Sachin Watta |  |  |  | 1 | 1 | 1 | 2 | 2
10 | 35 | impetus_sprint35 | DEV-39503 | Admin Tools | 7.6.8 | Unresolved | In Progress | Praveen Kumar |  |  |  |  | 2 |  |  | 3
11 | 35 | html_printing, impetus_sprint35 | DEV-39476 | Sign-Out | 7.6.8 | Unresolved | Initial Review | Abhishek Kumar |  |  |  |  | 2 |  |  | 4
12 | 35 | impetus_sprint35 | DEV-39400 | Physician Portal | 7.6.8 | Verified | Final Review | Manoj Singh | Nitin Anand |  | Sprint34 |  | 2 | 2 | 2 | 3 | 3
13 | 35 | impetus_DEV, impetus_sprint35 | DEV-39280 | Admin Tools | 8.0.0 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 2 | 2 | 2 | 3 | 3
14 | 35 | impetus_sprint35 | DEV-39234 | CPOE | 7.6.8 | Verified | Final Review | Ankit Verma | Nitin Anand |  | Sprint34 |  | 2 | 2 | 2 | 4 | 4
15 | 35 | impetus_sprint35 | DEV-38662 | Visit Types | 7.7.0 | Verified | Final Review | Manoj Singh | Swati Narang |  |  |  | 2 | 2 | 2 | 3 | 4
16 | 35 | impetus_sprint35 | DEV-38625 | NoteWriter | 7.6.8 | Unresolved | Testing | Manoj Singh |  |  |  |  | 1 |  |  | 2
17 | 35 | impetus_sprint35 | DEV-38047 | Patient List Management | 7.6.8 | Verified | Final Review | Ankit Verma | Nitin Anand |  |  |  | 1 | 1 | 1 | 1 | 1
18 | 35 | impetus_sprint35 | DEV-37992 | NoteWriter | 7.6.8 | Verified | Final Review | Kumar Saurabh | Swati Narang |  |  |  | 2 | 2 | 2 | 3 | 4
19 | 35 | impetus_sprint35 | DEV-36810 | NoteWriter | 7.7.0 | Unresolved | Untestable | Praveen Kumar |  |  |  |  | 2 | 2 | 2 | 3 | 3
20 | 35 | impetus_sprint35 | DEV-36719 | Desktop Clinical Results | 7.6.8 | Unresolved | In Progress | Ankit Verma |  |  | Sprint34 |  | 2 |  |  | 5
21 | 35 | impetus_QA_Identified, impetus_sprint35 | DEV-34991 | Admin Tools | Declined Issues | Duplicate | Closed |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
22 | 35 | impetus_sprint35 | DEV-32657 | Schedule | 7.x-MaintenanceTriage | Unresolved | Initial Review | Praveen Kumar |  |  |  |  | 2 |  |  | 3
23 | 35 | impetus_sprint35 | DEV-32250 | Provider Directory | 8.0.0 | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 2 |  |  | 4
24 | 35 | impetus_sprint35 | DEV-31351 | Desktop Clinical Results | 7.6.9 | Unresolved | In Progress | Suhani Aneja |  |  | Actual Size/Days 3/5 |  | 1 |  |  | 2
25 | 35 | impetus_sprint35 | DEV-31251 | Desktop Clinical Results | 7.6.9 | Unresolved | In Progress | Suhani Aneja |  |  | Actual Size/Days 3/5 |  | 1 |  |  | 2
26 | 35 | impetus_QA_Identified, impetus_sprint35 | DEV-30741 | NoteWriter | Declined Issues | Obsolete | Closed |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
27 | 35 | impetus_sprint35 | DEV-22052 | System/Mobilizer | 7.x-MaintenanceTriage | Unresolved | Open | Kumar Saurabh |  |  |  |  | 2 |  |  | 4
28 | 35 | html_printing, impetus_sprint35 | DEV-15125 | Sign-Out | 7.6.9 | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 3 |  |  | 6
29 | 35 | impetus_sprint35 | DEV-13122 | Physician Portal | 7.6.8 | Verified | Final Review | Ankit Verma | Sachin Watta |  |  |  | 2 | 2 | 2 | 3 | 3
30 | 35 | impetus_QA_Identified, impetus_sprint35 | DEV-13118 | Physician Portal | Declined Issues | Declined | Nothing to Fix |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
31 | 35 | impetus_QA_Identified, impetus_sprint35 | DEV-12648 | Desktop Clinical Results | Declined Issues | Declined | Nothing to Fix |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
32 | 35 | impetus_QA_Identified, impetus_sprint35 | DEV-12560 | Other (not included in this list) | 76x_FFD | Working as Designed | Closed |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
33 | 35 | impetus_QA_Identified, impetus_sprint35 | DEV-10329 | Desktop Clinical Results | Declined Issues | Declined | Nothing to Fix |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
1 | 36 | html_printing, impetus_sprint36 | DEV-39815 | Desktop Clinical Results | 7.6.9 | Unresolved | Open | Abhishek Kumar |  |  |  |  | 2 |  |  | 3
2 | 36 | impetus_sprint36 | DEV-39812 | System/Mobilizer | 7.6.9 | Verified | Final Review | Kumar Saurabh |  |  |  |  | 1 | 1 | 1 | 2 | 2
3 | 36 | impetus_sprint36 | DEV-39770 | NoteWriter | NWIPAD | Unresolved | Open | Abhishek Kumar |  |  |  |  | 2 |  |  | 3
4 | 36 | impetus_sprint36 | DEV-39683 | NoteWriter | Maintenance Backlog | Unresolved | In Progress | Manoj Singh |  |  |  |  | 1 |  |  | 2
5 | 36 | impetus_sprint36 | DEV-39661 | Admin Tools, NoteWriter | 7.6.8 | Unresolved | Testing | Manoj Singh |  |  |  |  | 1 |  |  | 1
6 | 36 | impetus_sprint36 | DEV-39660 | Admin Tools | 7.6.9 | Verified | Final Review | Ankit Verma |  |  |  |  | 1 | 1 | 1 | 1 | 1
7 | 36 | impetus_sprint36 | DEV-39659 | Admin Tools, NoteWriter | 7.6.8 | Unresolved | Testing | Manoj Singh |  |  |  |  | 1 |  |  | 2
8 | 36 | impetus_sprint36 | DEV-39656 | Desktop Clinical Results | 7.6.8 | Verified | Final Review | Praveen Kumar |  |  |  |  | 1 | 1 | 1 | 2 | 2
9 | 36 | impetus_sprint36, notewriter | DEV-39557 | NoteWriter | 7.6.8 | Verified | Final Review | Abhishek Kumar |  |  |  |  | 1 | 1 | 1 | 2 | 2
10 | 36 | impetus_sprint35, impetus_sprint36 | DEV-39503 | Admin Tools | 7.6.9 | Unresolved | In Progress | Praveen Kumar |  |  |  |  | 1 |  |  | 2
11 | 36 | html_printing, impetus_sprint36 | DEV-39475 | Sign-Out | 7.6.8 | Verified | Final Review | Abhishek Kumar |  |  |  |  | 1 | 1 | 1 | 2 | 2
12 | 36 | impetus_sprint36 | DEV-39463 | Sign-Out | 7.6.9 | Verified | Final Review | Ankit Verma |  |  |  |  | 1 | 1 | 1 | 1 | 1
13 | 36 | impetus_sprint36 | DEV-39427 | Desktop Clinical Results | Maintenance Backlog | Unresolved | Initial Review | Kumar Saurabh |  |  |  |  | 1 |  |  | 2
14 | 36 | impetus_DEV, impetus_sprint36 | DEV-39352 | Admin Tools | MOB_768_FFD | Verified | Final Review | Suhani Aneja |  |  |  |  | 1 | 1 | 1 | 2 | 2
15 | 36 | impetus_sprint36 | DEV-39240 | CPOE | 7.6.8 | Verified | Final Review | Praveen Kumar | Sachin Watta |  |  |  | 1 | 1 | 1 | 2 | 2
16 | 36 | impetus_sprint36 | DEV-38625 | NoteWriter | 7.6.8 | Verified | Final Review | Manoj Singh | Sachin Watta |  |  |  | 1 | 1 | 1 | 2 | 2
17 | 36 | impetus_sprint36 | DEV-37946 | Admin Tools | 7.6.9 | Verified | Final Review | Ankit Verma |  |  |  |  | 2 | 2 | 2 | 3 | 3
18 | 36 | impetus_sprint36 | DEV-37832 | Admin Tools, System/Mobilizer | 7.6.3 | Verified | Final Review | [5 empty] | 0 | 0 | 0 | 0 | 0
19 | 36 | impetus_sprint36 | DEV-37823 | Admin Tools, Desktop Clinical Results | MOB_768_FFD | Unresolved | In Progress | Kumar Saurabh |  |  |  |  | 2 |  |  | 4
20 | 36 | impetus_sprint36 | DEV-37721 | Charge Capture | 7.6.4 | Duplicate | Closed | [5 empty] | 0 | 0 | 0 | 0 | 0
21 | 36 | Partners, impetus_DEV, impetus_sprint36 | DEV-37137 | Admin Tools | MOB_768_FFD | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 1 |  |  | 2
22 | 36 | impetus_sprint36 | DEV-36719 | Desktop Clinical Results | 7.6.8 | Verified | Final Review | Ankit Verma |  |  |  |  | 2 | 2 | 2 | 4 | 4
23 | 36 | impetus_sprint36 | DEV-35409 | Physician Portal | Declined Issues | Workaround Provided | Final Review | [5 empty] | 0.8 | 0.8 | 0.8 | 1 | 1
24 | 36 | impetus_sprint36 | DEV-32250 | Provider Directory | 8.0.0 | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 2 |  |  | 4
25 | 36 | impetus_sprint36 | DEV-27678 | Charge Capture, iPhone | Declined Issues | Not Reproducible | Closed | [5 empty] | 0 | 0 | 0 | 0 | 0
26 | 36 | impetus_sprint36 | DEV-23728 | Charge Capture, iPhone, Mobile Clinical Results, Patient List Management | Declined Issues | Obsolete | Closed | [5 empty] | 0 | 0 | 0 | 0 | 0
27 | 36 | impetus_QA_Identified, impetus_sprint36 | DEV-14818 | Admin Tools | Declined Issues | Obsolete | Closed |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
28 | 36 | impetus_QA_Identified, impetus_sprint36 | DEV-14384 | Messaging | Declined Issues | Declined | Closed |  | Sachin Watta |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
29 | 36 | impetus_QA_Identified, impetus_sprint36 | DEV-12511 | Admin Tools | Declined Issues | Obsolete | Closed |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
30 | 36 | impetus_QA_Identified, impetus_sprint36 | DEV-12081 | Admin Tools | Declined Issues | Declined | Nothing to Fix |  | Sachin Watta |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
31 | 36 | impetus_sprint36 | DEV-11404 | Charge Capture | 7.6.1 | Duplicate | Closed | [5 empty] | 0 | 0 | 0 | 0 | 0
1 | 37 | impetus_sprint37 | DEV-40040 | Charge Capture, Patient List, Physician Portal | 7.6.9 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
2 | 37 | impetus_QA_Analysis, impetus_sprint37 | DEV-39980 | Dispatcher | 7.6.8 | Verified | Final Review | Praveen Kumar | Sachin Watta |  |  |  | 1 | 1 | 1 | 1 | 1
3 | 37 | impetus_QA_Analysis, impetus_sprint37 | DEV-39913 | eSignature | MOB_768_FFD | Unresolved | Initial Review | Praveen Kumar |  |  |  |  | 2 |  |  | 3
4 | 37 | impetus_DEV, impetus_sprint37 | DEV-39909 | Desktop Clinical Results | Maintenance Backlog | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 2 |  |  | 3
5 | 37 | impetus_sprint37 | DEV-39902 | NoteWriter | 7.6.9 | Unresolved | In Progress | Ankit Verma |  |  |  |  | 2 |  |  | 3
6 | 37 | impetus_sprint37 | DEV-39901 | Admin Tools | 7.6.9 | Verified | Final Review | Ankit Verma | Sachin Watta |  |  |  | 1 | 1 | 1 | 2 | 2
7 | 37 | impetus_sprint37 | DEV-39899 | NoteWriter | 7.6.9 | Verified | Final Review | Kumar Saurabh | Sachin Watta |  |  |  | 1 | 1 | 1 | 2 | 2
8 | 37 | impetus_sprint37 | DEV-39898 | Physician Portal | MOB_768_FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
9 | 37 | impetus_sprint37 | DEV-39862 | Admin Tools, NoteWriter | 7.6.9 | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
10 | 37 | impetus_sprint37 | DEV-39835 | CPOE | 7.6.9 | Unresolved | Open | Suhani Aneja |  |  |  |  | 2 |  |  | 3
11 | 37 | html_printing, impetus_sprint37 | DEV-39815 | Desktop Clinical Results | MOB_768_FFD | Verified | Final Review | Abhishek Kumar | Sachin Watta |  |  |  | 2 | 2 | 2 | 3 | 4
12 | 37 | impetus_sprint37 | DEV-39770 | NoteWriter | NWIPAD | Verified | Final Review | Abhishek Kumar | Sachin Watta |  |  |  | 2 | 2 | 2 | 3 | 3
13 | 37 | QT, impetus_sprint37 | DEV-39765 | Admin Tools, NoteWriter | MOB_768_FFD | Unresolved | In Progress | Praveen Kumar |  |  |  |  | 1 |  |  | 2
14 | 37 | impetus_sprint37 | DEV-39764 | Admin Tools, NoteWriter | 7.6.9 | Verified | Final Review | Kumar Saurabh | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
15 | 37 | impetus_sprint37 | DEV-39763 | Admin Tools, NoteWriter | 7.6.9 | Unresolved | Final Review | Kumar Saurabh | Sachin Watta |  |  |  | 2 | 2 | 2 | 3 | 3
16 | 37 | impetus_sprint37 | DEV-39683 | NoteWriter | Maintenance Backlog | Unresolved | In Progress | Manoj Singh |  |  |  |  | 1 |  |  | 2
17 | 37 | impetus_sprint37 | DEV-39661 | Admin Tools, NoteWriter | 7.6.8 | Verified | Final Review | Manoj Singh | Sachin Watta |  |  |  | 2 | 2 | 2 | 3 | 3
18 | 37 | impetus_sprint37 | DEV-39659 | Admin Tools, NoteWriter | 7.6.8 | Verified | Final Review | Manoj Singh | Sachin Watta |  |  |  | 2 | 2 | 2 | 5 | 5
19 | 37 | impetus_sprint35, impetus_sprint36, impetus_sprint37 | DEV-39503 | Admin Tools | MOB_768_FFD | Verified | Final Review | Praveen Kumar | Nitin Anand |  |  |  | 2 | 2 | 2 | 5 | 5
20 | 37 | html_printing, impetus_sprint37 | DEV-39484 | Sign-Out | MOB_768_FFD | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 1 |  |  | 2
21 | 37 | html_printing, impetus_sprint37 | DEV-39476 | Sign-Out | MOB_768_FFD | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 1 |  |  | 2
22 | 37 | impetus_sprint37 | DEV-39427 | Desktop Clinical Results | MOB_768_FFD | Unresolved | In Progress | [5 empty] | 1 |  |  | 2
23 | 37 | impetus_sprint37 | DEV-39414 | CPOE | 7.6.9 | Verified | Final Review | Ankit Verma | Sachin Watta |  |  |  | 1 | 1 | 1 | 1 | 2
24 | 37 | impetus_sprint37 | DEV-38646 | Admin Tools | MOB_768_FFD | Unresolved | In Progress | Manoj Singh |  |  |  |  | 1 |  |  | 2
25 | 37 | impetus_sprint37 | DEV-37823 | Admin Tools, Desktop Clinical Results | MOB_768_FFD | Verified | Final Review | Kumar Saurabh | Sachin Watta |  |  |  | 2 | 2 | 2 | 5 | 5
26 | 37 | Partners, impetus_sprint37 | DEV-37137 | Admin Tools | MOB_768_FFD | Verified | Final Review | Suhani Aneja | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
27 | 37 | impetus_QA_Identified, impetus_sprint37 | DEV-36061 | CPOE, Order Sets | 7.6.9 | Not Reproducible | Nothing to Fix |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
28 | 37 | impetus_sprint37 | DEV-24314 | Physician Portal | Declined Issues | Working as Designed | Closed | Suhani Aneja | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
29 | 37 | html_printing, impetus_sprint37 | DEV-15125 | Sign-Out | MOB_768_FFD | Unresolved | In Progress | Abhishek Kumar |  |  |  |  | 2 |  |  | 4
30 | 37 | impetus_QA_Identified, impetus_sprint37 | DEV-14182 | Admin Tools | Declined Issues | Declined | Closed |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
1 | 38 | impetus_DEV, impetus_sprint38 | DEV-40044 | CPOE | 7.6.9 | Unresolved | Initial Review | Suhani Aneja |  |  |  |  | 0.8 |  |  | 1
2 | 38 | PM_clarification_needed, impetus_sprint38 | DEV-40037 | Physician Portal | MOB_768_FFD | Unresolved | In Progress | Ankit Verma |  |  |  |  | 1 |  |  | 2
3 | 38 | impetus_sprint38 | DEV-39990 | Sign-Out | 8.0.0 | Unresolved | Initial Review | Abhishek Kumar |  |  |  |  | 1 |  |  | 2
4 | 38 | impetus_QA_Analysis, impetus_sprint38 | DEV-39943 | Admin Tools | MOB_768_FFD | Unresolved | Initial Review | Ankit Verma
5 | 38 | impetus_QA_Analysis, impetus_sprint37, impetus_sprint38 | DEV-39913 | eSignature | MOB_768_FFD | Verified | Final Review | Praveen Kumar | Nitin Anand |  |  |  | 1 | 1 | 1 | 2 | 2
6 | 38 | impetus_DEV, impetus_sprint38 | DEV-39909 | Desktop Clinical Results | Maintenance Backlog | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 1 |  |  | 2
7 | 38 | impetus_sprint38 | DEV-39835 | CPOE | 7.6.9 | Unresolved | Open | Suhani Aneja |  |  |  |  | 2 |  |  | 3
8 | 38 | impetus_sprint38 | DEV-39683 | NoteWriter | Maintenance Backlog | Unresolved | In Progress | Manoj Singh |  |  |  |  | 2 |  |  | 3
9 | 38 | html_printing, impetus_sprint37, impetus_sprint38 | DEV-39484 | Sign-Out | MOB_768_FFD | Unresolved | Testing | Abhishek Kumar |  |  |  |  | 1 |  |  | 2
10 | 38 | html_printing, impetus_sprint37, impetus_sprint38 | DEV-39476 | Sign-Out | MOB_768_FFD | Unresolved | Testing | Abhishek Kumar |  |  |  |  | 1 |  |  | 2
11 | 38 | impetus_DEV, impetus_sprint38 | DEV-39305 | Physician Portal | Maintenance Backlog | Unresolved | In Progress | Suhani Aneja |  |  |  |  | 0.8 |  |  | 1
12 | 38 | impetus_DEV, impetus_sprint38 | DEV-39261 | CPOE | 7.6.9 | Unresolved | Open | Suhani Aneja |  |  |  |  | 0.8 |  |  | 1
13 | 38 | impetus_sprint38 | DEV-39178 | CPOE | 7.6.10 | Unresolved | Open | Kumar Saurabh |  |  |  |  | 2 |  |  | 4
14 | 38 | impetus_QA_Identified, impetus_sprint38 | DEV-39122 | Patient List | Declined Issues | Obsolete | Closed |  | Nitin Anand |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
15 | 38 | impetus_QA_Analysis, impetus_sprint38 | DEV-38988 | Charge Capture | 8.0.0 | Unresolved | Initial Review | Praveen Kumar |  |  |  |  | 1 |  |  | 2
16 | 38 | impetus_QA_Analysis, impetus_sprint38 | DEV-38514 | Charge Capture | 8.0.0 | Unresolved | Initial Review | Praveen Kumar |  |  |  |  | 2 |  |  | 2
17 | 38 | impetus_sprint38 | DEV-36832 | Admin Tools | 76x_FFD | Unresolved | Open | Kumar Saurabh |  |  |  |  | 2 |  |  | 3
18 | 38 | impetus_QA_Analysis, impetus_sprint38 | DEV-36294 | Admin Tools | MOB_768_FFD | Unresolved | Initial Review | Ankit Verma |  |  |  |  | 2 |  |  | 4
19 | 38 | html_printing, impetus_sprint34, impetus_sprint38 | DEV-34166 | Desktop Clinical Results | 7.7.0, MOB_768_FFD | Unresolved | Initial Review | Abhishek Kumar |  |  |  |  | 3 |  |  | 4
20 | 38 | impetus_sprint38 | DEV-32757 | Admin Tools | 76x_FFD | Unresolved | In Progress | Kumar Saurabh |  |  |  |  | 1 |  |  | 2
21 | 38 | impetus_sprint38 | DEV-31351 | Desktop Clinical Results | 8.0.0 | Unresolved | In Progress | Suhani Aneja |  |  |  | (Worked in Sprint34,35,36 as well) | 3 |  |  | 6
22 | 38 | impetus_sprint38 | DEV-31251 | Desktop Clinical Results | 8.0.0 | Unresolved | In Progress | Suhani Aneja |  |  |  | (Worked in Sprint34,35,36 as well) | 3 |  |  | 6
23 | 38 | impetus_sprint38 | DEV-19069 | NoteWriter | Future - to be scheduled | Declined | Nothing to Fix |  | Sachin Watta |  |  |  | 0.8 | 0.8 | 0.8 | 1 | 1
24 | 38 | html_printing, impetus_sprint37, impetus_sprint38 | DEV-15125 | Sign-Out | MOB_768_FFD | Verified | Final Review | Abhishek Kumar | Sachin Watta |  |  |  | 2 | 2 | 2 | 4 | 4
25 | 38 | impetus_sprint38 | DEV-10844 | Desktop Clinical Results | MOB_768_FFD | Unresolved | Open | Ankit Verma |  |  |  |  | 2 |  |  | 4

## Sprint Metrics
[6 empty] | Planned Size/Effort |  |  | Actual Size/Effort |  |  | Actual # Issues |  |  |  |  | QA Metrics
Sprint No | Sprint From | Sprint To | # Holidays | # Leaves (person days) | Available Dev Capacity (in Hrs) | Estimated Size (in Points) | Revised Size (in Points) | Estimated Effort (in Hrs) | Delivered Size (in Points) | Actual Effort (in Hrs referred from Timesheet) | Mapping Factor (Point -> Hrs) | # Issues Worked Upon | # Issues In Progress | # Issues Revisited | # Issues Completed | # Issues Testing | # Issues Tested / Closed by QA | # Defects Found by QA | # Test Case Created | Remarks (e.g. Challenges, Risk Factors etc)
1 | 2011-10-31 | 2011-11-15 |  | 2 | 391 | [6 empty] | 21 | 0 | 1 | 20 | 0 | 12 | 0 | 12 | 28494 re-assigned to Umesh
2 | 2011-11-16 | 2011-11-25 |  | 3 | 314.5 | [6 empty] | 22 | 0 | 1 | 22 | 0 | 20 | 2 | 23 | 24612 Fixed in Sprint04
3 | 2011-11-28 | 2011-12-14 |  | 4 | 518.5 | [6 empty] | 26 | 0 | 3 | 26 | 0 | 25 | 0 | 19
4 | 2011-12-15 | 2011-12-30 |  | 3 | 484.5 | [6 empty] | 25 | 0 | 3 | 25 | 0 | 12 | 0 | 20
5 | 2012-01-02 | 2012-01-20 |  | 2 | 620.5 | [6 empty] | 13 | 0 | 0 | 10 | 0 | 9 | 2 | 9 | 9351, 19655, 23200 were removed in sprint06
6 | 2012-01-23 | 2012-02-03 | 1 | 2 | 365.5 | [6 empty] | 21 | 0 | 1 | 17 | 0 | 12 | 1 | 12 | 10494 went to PMCN after working on this issue.
7 | 2012-02-06 | 2012-02-17 |  | 4 | 391 | [6 empty] | 31 | 0 | 1 | 31 | 0 | 11 | 2 | 11 | 29906 took 5 days, 27746 took 3 days of current sprint, 20 issues were resolved as HIMSS
8 | 2012-02-20 | 2012-03-02 |  | 3 | 399.5 | [6 empty] | 26 | 0 | 0 | 22 | 0 | 15 | 2 | 17
9 | 2012-03-05 | 2012-03-16 | 1 | 11 | 289 | [6 empty] | 24 | 0 | 0 | 14 | 0 | 11 | 3 | 1
10 | 2012-03-19 | 2012-03-30 |  | 4 | 391 | [6 empty] | 19 | 0 | 1 | 12 | 0 | 12 | 1 | 11 | DEV 19006 was worked upon the whole sprint
11 | 2012-04-02 | 2012-04-13 |  | 10 | 340 | [6 empty] | 16 | 0 | 1 | 10 | 0 | 7 | 1 | 5 | DEV 19006 was worked upon the whole sprint
12 | 2012-04-16 | 2012-04-27 |  | 6 | 374 | [6 empty] | 17 | 0 | 1 | 13 | 0 | 5 | 0 | 2 | DEV 19006 was worked upon the whole sprint
13 | 2012-04-30 | 2012-05-11 |  | 1 | 416.5 | 17.4 | 17.4 | 314.5 | 17.4 | 410 | 23.5632 | 22 | 0 | 0 | 17 | 0 | 17 | 3 | 29 | 18 Test Cases for HIMSS
14 | 2012-05-14 | 2012-05-25 |  | 1 | 416.5 | 24.8 | 26.8 | 399.5 | 23.8 | 417 | 17.521 | 23 | 0 | 1 | 20 | 0 | 15 | 9 | 6
15 | 2012-05-28 | 2012-06-08 |  | 10 | 340 | 25.8 | 25.8 | 425 | 25.6 | 340 | 13.2812 | 27 | 0 | 0 | 22 | 0 | 22 | 2 | 11 | Nitin worked on DEV-36148, Fixed 11 issues from Portal_facelift
16 | 2012-06-11 | 2012-06-22 |  | 13 | 314.5 | 24.2 | 23 | 374 | 21.8 | 310 | 14.2202 | 29 | 0 | 0 | 26 | 0 | 16 | 0 | 7
17 | 2012-06-25 | 2012-07-06 |  | 6 | 374 | 16.6 | 16.6 | 306 | 15.4 | 371 | 24.0909 | 29 | 0 | 0 | 19 | 0 | 15 |  | 8
18 | 2012-07-09 | 2012-07-20 |  | 1 | 416.5 | 16.8 | 15.8 | 246.5 | 18.8 | 413.5 | 21.9947 | 27 | 0 | 0 | 17 | 0 | 15 |  | 15
19 | 2012-07-23 | 2012-08-03 |  | 4 | 391 | 13.2 | 13.4 | 153 | 12.4 | 382 | 30.8065 | 23 | 0 | 0 | 13 | 0 | 7 |  | 7
20 | 2012-08-06 | 2012-08-17 | 1 | 9 | 306 | 14.8 | 16.8 | 297.5 | 14.8 | 300 | 20.2703 | 15 | 0 | 0 | 15 | 0 | 8 |  | 8
21 | 2012-08-20 | 2012-08-31 |  | 6 | 374 | 18 | 20 | 340 | 19.2 | 357 | 18.5938 | 18 | 0 | 0 | 16 | 1 | 10 |  | 10
22 | 2012-09-03 | 2012-09-14 |  |  | 340 | 17.8 | 17.8 | 314.5 | 15 | 329.5 | 21.9667 | 17 | 2 | 0 | 13 | 1 | 9 |  | 7
23 | 2012-09-17 | 2012-09-28 |  |  | 425 | 22.6 | 23.6 | 408 | 18.6 |  |  | 17 | 0 | 0 | 14 | 0 | 9 |  | 9
24 | 2012-10-01 | 2012-10-12 | 1 | 4 | 348.5 | 23.8 | 23.8 | 374 | 19.8 |  |  | 20 | 2 | 0 | 18 | 0 | 16 |  | 8
25 | 2012-10-15 | 2012-10-26 | 1 | 3 | 357 | 18.4 | 14.6 | 314.5 | 14.6 |  |  | 20 | 2 | 0 | 17 | 1 | 15 |  | 3
26 | 2012-10-29 | 2012-11-09 |  | 2 | 408 | 25.4 | 20.6 | 399.5 | 23.8 |  |  | 25 | 5 | 0 | 19 | 0 | 15 |  | 15
27 | 2012-11-12 | 2012-11-23 | 1 | 18 | 229.5 | 16.4 | 7.4 | 280.5 | 4.4 |  |  | 10 | 8 |  | 5 | 0 | 5 |  | 2
28 | 2012-11-26 | 2012-12-07 |  | 7 | 365.5 | 25.6 | 14.8 | 408 | 14.8 |  |  | 22 | 7 | 1 | 13 | 1 | 7 |  | 3
29 | 2012-12-10 | 2012-12-21 |  | 3 | 399.5 | 24.6 | 14.6 | 442 | 14.6 |  |  | 21 | 4 | 0 | 13 | 2 | 8 |  | 5
30 | 2012-12-24 | 2013-01-04 | 1 | 4 | 348.5 | 25.4 | 20.6 | 518.5 | 21.6 |  |  | 22 | 7 | 0 | 14 | 1 | 12 | 3 | 11
31 | 2013-01-07 | 2013-01-18 |  | 2 | 408 | 36.4 | 18.2 | 467.5 | 19.2 |  |  | 24 | 4 | 0 | 16 | 1 | 13 |  | 5
32 | 2013-01-21 | 2013-02-01 |  | 3 | 484.5 | 30.8 | 19.8 | 493 | 18.2 |  |  | 26 | 3 | 0 | 21 | 0 | 15 |  | 11 | fixed addiional DEV-39041,QA worked on two Nothing to Fix/Declined issues DEV-34352, DEV-34647
33 | 2013-02-04 | 2013-02-15 |  | 5 | 467.5 | 30.6 | 16.6 | 467.5 | 16.6 |  |  | 26 | 4 | 0 | 20 | 1 | 20 | 10 | 3 | QA identified 10 defects(Nothing to Fix/Declined)
34 | 2013-02-18 | 2013-03-01 |  |  | 510 | 44.2 | 18.4 | 705.5 | 18.4 |  |  | 26 | 9 | 0 | 16 | 1 | 14 | 0 | 5
35 | 2013-03-04 | 2013-03-15 |  | 3 | 484.5 | 47.2 | 26.2 | 663 | 26.2 | 493 | 18.8168 | 30 | 9 | 0 | 20 | 1 | 18 | 0 | 2
36 | 2013-03-18 | 2013-03-29 | 1 | 12 | 357 | 31 | 17 | 450.5 | 17 | 339.5 | 19.9706 | 24 | 5 | 0 | 21 | 0 | 21 | 9 | 4 | QA identified 4 defects(Nothing to Fix/Declined)
37 | 2013-04-01 | 2013-04-12 |  | 4 | 476 | 41 | 25 | 612 | 25 | 469.5 | 18.78 | 30 | 9 | 0 | 19 | 1 | 18 | 4 | 6
38 | 2013-04-15 | 2013-04-26 |  | 1 | 501.5 | 37 | 4.6 | 544 | 4.6 |  |  |  | 7 |  | 4 | 2 | 4 | 2
| Total |  |  |  | 11101 |  |  | 10174.5 | 457 | 3630 | 206.3084 |  |  |  | 526
| Average |  |  |  | 382.7931 |  |  | 406.98 | 18.28 | 363 | 20.6308 |  |  |  | 16.7576
[8 empty] | Till 15-Jan-13 | From 16-Jan-13
|  |  | # Dev Resources (Budgeted) |  |  |  |  | 4 | 5
|  |  | Hrs / resource / day |  |  |  |  | 8.5 | 8.5
|  |  | Budgeted Dev Capacity per 2-wk sprint (in Hrs) |  |  |  |  | 340 | 425
|  |  | # Dev Resources (Actual) |  |  |  |  | 5 | 6
|  |  | Analysis Time |  |  |  |  | 85 | 102
Info related to calculation of Points:
For Low issues - 0.8 pt = <1 day (average estimated effort = 1 day)
For Medium issues - 1 pt = 1-2 days (average estimated effort = 2 days)
For High issues - 2 pt = 3-5 days (average estimated effort = 4 days)
For Very High issues - 3 pt = >5 days (estimated effort will be pts * 2)
Note on T4: Sameer Panda: 5 Test Cases were created for issues directly assigned to QA by PK
Note on E21: Sameer Panda: 2 Saurabh, 1 Suhani, 1 Sameer
Note on D22: Sameer Panda: Independence Day 15 Aug
Note on E22: Sameer Panda: 6 Abhishek, 1 Praveen, 2 Sameer

## Dashboard
Development Metrics
QA Metrics

## Team Commitment (hidden)
| Name | Sameer |  | Praveen |  | Saurabh |  | Suhani |  | Abhishek
Sprint |  | Commited | Actual | Commited | Actual | Commited | Actual | Commited | Actual | Commited | Actual
Sprint 12 |  | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 4 | 1 | 0
Sprint 13 |  | 4 | 5 | 4 | 3 | 4 | 2 | 4 | 4 | 4 | 3
Sprint 14 |  | 2 | 3 | 3 | 4 | 3 | 3 | 3 | 4 | 3 | 6
Sprint 15 |  | 0 | 0 | 4 | 5 | 4 | 6 | 4 | 4 | 5 | 7
Sprint 16 |  | 4 | 3 |  |  | 4 |  | 4 |  | 7
Sprint 17
Sprint 18
Sprint 19
Sprint 20
Sprint 21
Sprint 22
Sprint 23
Sprint 24
Sprint 25
Sprint 26
Sprint 27
Sprint 28
Sprint 29
Sprint 30
Sprint 31
Sprint 32
Sprint 33

## Retrospectives
Sprint 12
What went well? |  | Guidelines: 1) What went well, that we want to continue doing in next sprints? 2) What did not go well, that we want to avoid? 3) What could be improved? Did we achieve the sprint goal? Are the decisions taken in the retrospective meeting of the pre
1 | Fixing of DEV 19006
2 | DEV completion of HIMSS issues into MOB 760 Branch.
3 | Interaction between the Impetus and PK team.
What did not go well?
1 | The overall team commitment was not met.
What could be improved?
1 | Information on JIRA issues.
2 | Early Q&A sessions.
3 | Larger Product Backlog.
4 | Planning the task in the first 2 days of sprint
Sprint 13
What went well?
1 | Sprint planning.
What did not go well?
1 | Analysis of few issues.
What could be improved?
1 | Create extra bucket of issues after analysis.
2 | QA needs to analyze the issue from testing prespective.
3 | While providing estimation keep bandwidth for Revisit issues.
4 | Update JIRA comments as and when available.
Sprint 14
What went well?
1 | Creation of extra bucket of issues after analysis.
2 | QA analyzed the issue from testing prespective.
3 | The estimation were provided alongwith the bandwidth for Revisit issues.
4 | Updated JIRA comments as and when available.
What did not go well?
1 | Unstable 7.6.0 Environment
What could be improved?
1 | JIRA comments containing info related to impacted areas.
Sprint 15
What went well?
1 | Sprint Analysis and Planning
2 | Deliveries were in accordance to the commitments
What did not go well?
What could be improved?
1 | Worklog entered to be more actual to the number of hours spent on dev issues.
2 | Dev issues without SF needs to be discussed.
Sprint 22
What went well?
1 | Team enhanced their product knowledge while working on various enhancements like upgrade task,audit hcarge,web xml customization,billing monitor thread
2
3
4
What did not go well?
1 | The overall team commitment was not met.
2
3
What could be improved?
1 | larger backlog having simple and complex issues
2
3
Sprint 23
What went well?
1 | Team worked on major enhancement like adding filter criteria on charge search, web customization applicable to different level of users
2 | Team worked on dispatcher issues
3
What did not go well?
1
2
3
What could be improved?
1
2
3
Sprint 24
What went well?
1 | Team enhanced their product knowledge while working on various components like NoteWriter,Charge Capture.
2 | worked on major enhancement like DEV-10319
3
What did not go well?
1
2
3
What could be improved?
1
2
3
MOM
1 | QA needs to be cautious while verifying Nothing To Fix/Not Reproducible issues.
2
3
Sprint 31
What went well?
1 | Team enhanced their product knowledge while working on NoteWriter issues.
2 | worked on DEV-35383, adding the ability to the Man Reg Screen to have multiple(1…n) Dynamic Fields(Text/Dropdown) which can be ADD/DELETED/UPDATED, within the given time constraint
3 | added new fucntionality of removing vitals
4 | Team member Worked upon on 7.7.0 merged conflict issue and able to resolve that successfully
5 | added new favorite modifier popup functionality over charge
What did not go well?
1
2
3
What could be improved?
1
2
3
MOM
1 | QA needs to be cautious while verifying Nothing To Fix/Not Reproducible issues.
2
3
Sprint 35
What went well?
1 | CPOE Routing configuration at local and QA environment
2 | Converted Html printing to PDF printing for Test Result module
3 | Delivered 20 issues in Sprint 35
4 | Team worked upon 7.6.8 release items
5 | Major work in Note Writer Module by creating a new template for DEMO purpose.
6 | Worked upon Major enhancement like 31251,32522
What did not go well?
1 | Patch for two 7.6.9 defects is ready, waiting for 7.6.9 branch to check-in the code
2
3
What could be improved?
1 | Larger backlog of simple and complex issues
2
3
MOM
1 | QA need to take care for impacted areas while testing of defects
2 | Dev team member need to make sure that whatever chanes they do in code should not break existing logic or flow
3 | QA will perform testing on Safari/Mac Machine as well with IE 8 Browser for both the QA Environments (non custom/custom mobilizer)
4 | team need to work on 7.6.8 items on high priority
Sprint 36
What went well?
1 | team worked upon CPOE and NoteWriter issues
2 | team worked upon 7.6.8 and 7.6.9 release items
3 | Delivered 21 issues in Sprint 36
4 | Number of defects analyzed by QA : 31
5 | Number of defects closed by QA in initial Analysis : 4
6 | Number of defects verified & closed by QA in Browser IE & Mac/Safari : 21
7 | Number of new defects in Jira while verification sprint defects/Regression testing in Browser IE & Mac/Safari : 9
8 | Number of Created Test cases for sprint36 : 2
What did not go well?
1 | Due to 7.6.8 build failure on Monday, QA could not verify two 7.6.8 defects
2
3
What could be improved?
1 | Larger backlog of simple and complex issues
2 | There are 39 issues in impetus_DEV are 39, which are already analyzed
3 | There are 35 issues in impetus_next for analysis
MOM
1 | impacted area matrix link is available at https://confluence/display/dedsus/Impetus+QA+Impact+Analysis+Matrix.
2 | team will work on 7.6.9 items on priority basis for sprint37
3 | team will take priority over defects defects rather than enhancement for 7.6.9 items
Sprint 37
What went well?
1 | In this sprint our most of the issues were from Note Writer.
2 | Delivered 19 issues in Sprint 37
3 | Number of defects verified & closed by QA in Browser IE & Mac/Safari : 19
4 | Number of new defects in Jira while verification sprint defects/Regression testing in Browser IE & Mac/Safari : 5
What did not go well?
1 | there were some issues got revisited in sprint37
2
3
What could be improved?
MOM
1 | For Level3 users, we will be supporting all major browsers with different resolutions.(as QA have)
2 | For other level users, we will support IE and Safari with standard resolution. If fix requires major effort then QA will log a new defect for browser compatibility(after taking confirmation from John/Umesh/PM) .
3 | Find items with Must have from Next release(7.6.9/8.0.0).
4 | Find items from next release which are not assigned to developer yet
5 | Find items with label as impetus_next
6 | fixVersion = "7.6.9" and assignee in (prodmgr, ichubarov,uphirke) and component not in (iPhone,"Meditech MIM Bridge")
7 | Backlog item PM priority for items is required.
8 | For Level3 users, we will be supporting all major browsers with different resolutions.(as QA have).